|  | EUROPEAN COMMISSION Directorate-General for Education and Culture Youth, sport and citizenship Citizenship policy: "Europe for Citizens" |
| --- | --- |

EFCC/70/2008-EN

Brussels, 20 May 2008

EAC D4/

Report on the activities under the "Europe for Citizens" programme 2007

# 1. Introduction

The aim of this document is to inform on the implementation of the programme "Europe for Citizens" in 2007. The report therefore describes the programme activities initiated based on the 2007 work programme, on which the programme committee had delivered a favourable opinion on 12 October 2006.

The year 2007 was the start of the new programme and consequently some measures could not be implemented for budgetary reasons (studies) and some measures were developed to be launched in 2008 (citizens' projects, support measures). The first projects within the new programme began as of 1 May 2008 whilst most activities started during the second semester. Therefore observations concerning the results and impact of the activities are of preliminary character: further evidence will be available when more activities have been concluded and reported back.

# 2. Political context and priorities

The Commission held a series of consultation meetings with the stakeholders in 2006 to discuss the most important issues of the programme implementation. Based on these consultations it was agreed that the programme implementation will be guided by a combination of permanent and annual priorities.

The permanent priorities guide and encourage the beneficiaries to work on long lasting basis on issues directly linked to the objectives of the programme. This creates the critical mass of activities around the core issues of the programme and it is expected to support thematic networking between the beneficiaries. The following five permanent priorities have been established:

- Future of the European Union and its basic values;

- Active European citizenship: participation and democracy in Europe;

- Intercultural dialogue

-People's well being in Europe: employment, social cohesion and sustainable development

- Impact of EU policies in societies.

The annual priorities are used to mobilise the beneficiaries to deal with the most topical European issues and exercises related to the permanent priorities. The annual priorities thus don't replace but complement and specify the permanent priorities.

In 2007 the annual priorities gave focus to the following issues:

- European Year 2007: Equal opportunities for all;

- Enlargement: getting to know the two new Member States.

- The European Year of intercultural dialogue

- 50th anniversary of the Treaty of Rome

As part of this political context, the developments in the sport and communication fields in 2007 shaped the environment of the active citizenship policy. In July 2007, the Commission adopted the White Paper on Sport. It highlighted the potential of sport in encouraging active citizenship, in particular to promote voluntary work,, social inclusion, integration and equal opportunities and referred to the role of the Europe for Citizens programme in this respect.  This was taken into account when developing the 2008 priorities for the Europe for Citizens programme.

As regards communication, the Plan D, aiming at strengthening dialogue, debate and democracy in Europe, was still in full swing in 2007. This exercise is by definition closely related to our 1st permanent priority. The institutional context changed with the adoption of the Lisbon Treaty, but the importance of dialogue, debate and democracy remains. Some of the key beneficiaries of the Europe for Citizens programme have been particularly actively involved at the European level in the plan D process, which has provided good opportunities to transfer knowledge between the two exercises.

# 3. Implementation of the "europe for Citizens" Programme

2007 was a year in which a double objective has been met: on the one hand, insuring continuity; on the other hand, launching a new programme which is more coherent and politically more ambitious. Indeed, the "Europe for the citizens" programme with its new features was launched while insuring a smooth transition from the previous programme.

The year 2007 involved also progress in terms of structuring a permanent dialogue with civil society organisations in the field. As a result new visibility and dynamism has been created  around the programme and around the theme "active European citizenship". Consequently first programme impacts have clearly been achieved in 2007 already.

Most of the actions of the programme have been implemented as from this first year on the basis of the programme guide as a "permanent call for proposals" and in some cases by means of specific calls for proposals. In 2007, a total of 2.252 grant applications were received and 1.125 projects/organisations selected.

Thematically, the focus concentrated on the following issues:

-	Intercultural dialogue (718 selected projects);

-	Active European Citizenship, participation and democracy (397 selected projects);

-	Equal opportunities (250 selected projects);

-	Social cohesion (225 selected projects);

-	Sustainable development (196 selected projects).

The focus varied slightly between the different actions and measures: in town twinning the issues of intercultural dialogue scored as highest, for civil society projects the top issue was Active European Citizenship, participation and democracy whilst for remembrance projects the European values came as first.

The above indicates that the thematic priorities are a success in terms of having been taken up by the participants and creating a critical mass of activities around the most topical issues. The networking impact is to be observed in long term.

3.1.	Action 1 – Active Citizens for Europe

Under Action 1, in 2007, the Town Twinning measure was implemented. It consisted of two sub-measures: "Town twinning Citizens' meetings" and "Thematic networking of twinned towns". Furthermore structural support was provided for the Council of European Municipalities and Regions (CEMR) as designated organisation.

- Town twinning Citizens meetings

Town twinning citizens’ meetings consist in bringing together a wide range of citizens and citizens’ groups from twinned towns, taking benefit of the partnership between the municipalities for developing strong, informal and personal relations between their citizens. The meetings combine an informal character emphasizing the "learning by doing" approach with thematic focus according to the programme priorities.

This measure involves many projects and many participants - its impact comes partly through the volume of direct participation of citizens. In 2007, 1.648 applications were introduced and 904 selected (acceptance rate: 55%).

Data presented by the selected beneficiaries show that some 71.000 citizens were expected to move across Europe to participate in a town twinning meeting in another country within the co-financed projects. Beside the mobile participants, many more have been involved as local participants. Indeed according to the project proposals 675.000 citizens altogether were expected to be involved in the selected projects. It is through them all that the programme meets the objective of "bringing together people from local communities across Europe to share and exchange experience, opinions and values".

France, Germany, Italy, Hungary and Poland are the most active countries to host citizens meetings. The geographic impact of the projects goes however beyond the host country – every project involves citizens from invited town(s) from other country/countries. For this reason one of the quantitative priorities is to encourage more multilateral citizens meetings. The evolution in this respect is positive: in 2007, 46% of the town twinning citizens meetings were multilateral, thus involving at least 3 towns from 3 different countries. The comparative figure in 2006 was 40 %. An other important indicator on the geographic impact of the measure is that in 2007 54% of the projects involved citizens of Member States which have acceded the EU in 2004 or later either. The comparative figure in 2006 was 47%. This marks a clear progress in line with the programme objectives.

- Thematic networking of twinned towns

A large number of municipalities in Europe are twinned to other towns, which might be themselves twinned to further towns. The measure "thematic networking of twinned towns" aims at using this potential of the networks created by a series of town twinning links for developing thematic cooperation between twinned towns. Such a co-operation enables the participating towns to develop, structure, and strengthen the strategic dimension of town twinning.

At the level of the Community programme thematic networking is a structuring measure, which extends the dimension of town twinning from people to people meetings to more informed discussions and systematic exchange of good practices.

In 2007, 89 applications were introduced and 52 selected (acceptance rate 58%). It appears that further efforts are needed in view of explaining and developing the potential of the concept together with the potential beneficiaries.

- Structural support for and dialogue with CEMR

The Council of European Municipalities and Regions – an organisation designated for an operating grant by the Europe for Citizens programme decision – has a privileged position in terms of representing the town twinning movement towards the European Commission. For this reason the Commission holds a regular dialogue with the CEMR to get feedback from the field and to exchange views concerning the future development of the action. In 2007 this dialogue had an additional specific character: the Commission co-operated closely with the CEMR in the context of the Rhodes conference highlighting the launch of the new programme.

3.2.	Action 2 – Active Civil Society in Europe

This action is targeted at civil society, in particular with the objective to foster action, debate and reflection related to European citizenship and democracy, shared values, common history and culture through cooperation amongst civil society organisations at European level. This action consists of 3 measures.

- Structural support for European public policy research organisations (think tanks)

This measure is aimed at strengthening the institutional capacity of European public policy research organisations (think tanks), which are able to provide new ideas and reflections on European issues, on active European citizenship or on European values.

In 2007 think tanks were for the first time supported under a specific measure. Operating grants were awarded for 13 organisations including the Notre Europe and Institut für Europäische Politik, designated in the basic act.  Out of the 13 organisations 11 had already received an operating grant under the previous programme, while two “new” organisations were supported in 2007. This represents a good balance between continuity and openness to newcomers, thus developing and strengthening partnerships while keeping the door open for new organisations.

For think tanks the participation in the programme was a stimulus to promote wider contacts across Europe, to work on key concepts in the area of active European citizenship such as the role and functioning of the European democratic structure and citizens' participation.

- Structural support for civil society organisations at European level

This measure provides civil society organisations of European dimension with better capacity and stability to develop their activities at European level. The purpose is to contribute to the emergence of a structured and active civil society at European level.

In 2007, structural support was awarded for 17 civil society organisations at European level including the organisations designated in the basic act, Social Platform, European Movement International and European Council on Refugees and Exiles (ECRE). Also for this measure a balance between continuity and openness was achieved with five newcomers in 2007.

In line with the horizontal nature of the programme the supported organisations cover a wide range of themes and activities. A common feature is that they all work on methodologies to boost citizens' participation in European context. It is thus valuable and essential that the results of their work are shared with other stakeholders in the field.

In 2007 relatively many applications for operating grants were received from organisations which did not accurately correspond to the profile targeted by the call for proposals. A challenge for the future is therefore to better explain this aspect to all stakeholders.

- Support for projects initiated by civil society organisations

The aim of this measure is to support cooperation on concrete projects of civil society organisations from different participating countries. A variety of organisations, established at local, regional, national or European level, can be involved.

In 2007, 197 applications were received and 108 projects selected with an acceptance rate of 55%. Geographically, the most active countries are Italy, Belgium, Germany, France and Hungary. The proportion of selected projects from the Member States which have acceded in the EU in 2004or after was  34%. This constitutes an important increase in comparison to the previous year, when the rate was 19%.

Within the new programme the civil society projects entered into a new phase: all projects have a trans-national dimension. This feature underlines the European character of the projects and increases significantly their impact. The new requirement was clearly positively received by the organisations in the field.

In 2007 many projects included trans-national seminars and conferences initiating reflection and debate on European issues. In view of increasing the impact of the measure, an important challenge for the future is to encourage a bigger variety of projects, including those of concrete productions or realisation as well as those of thematic networking.

3.3.	Action 3 – Together for Europe

In 2007, special attention was paid to the launching events and communication on the new programme.

- High visibility events

During the year 2007 two high visibility events were organised.

The launch event of the programme in May in Rhodes/Brussels:

The launch event was composed by two parallel activities: a round table debate in Brussels and a conference in Rhodes organized by CEMR assembling some 500 participants from the town-twinning field.

In Brussels, a discussion involving Commissioner Figel and high profile political personalities focused around the main 4 objectives of active citizenship, namely participation, identity, ownership of the EU, tolerance and mutual understanding. In Rhodes, the conference focused on the future challenges and opportunities in the field of town twinning including the new possibilities to co-operate with the civil society organisations in the framework of the Europe for Citizens programme.

The two events were connected for 15 minutes through a satellite conference, which created a symbolic momentum highlighting the political importance of the launch of the new programme.

The "Europe for Citizens" Forum 2007 and Golden Stars Awards:

The annual Europe for Citizens forum was organised in November 2007 in Brussels under the title: "Europe for Citizens forum – together for intercultural dialogue". The presence of approximately 350 participants, the vivid interest shown for the theme and the very active interaction between participants and speakers confirmed the choice to build this annual event around themes of the moment.

The exhibition on the 10 Golden Stars projects and the award ceremony offered additional possibilities for networking. Broad media coverage – in 13 Member States – was achieved through the presence of press linked to the Golden Star winners.

- Information and dissemination tools

As 2007 was the first year of the programme, it was especially important to give a proper place to information and dissemination tools. The following were made available in the course of that year:

- Promotional/Information material:

Posters (multilingual); leaflets on the "Europe for Citizens" Programme (EN, FR, DE - all languages will be covered in the future); postcards on the "Europe for Citizens" Programme (EN, FR, DE - all languages will be covered in the future); pens, bloc-notes, post-it, page-markers….

- Brochures:

Production of the "Thematic networking of twinned towns" brochure (available in EN, FR, DE, IT, ES, PL)

Production of the "Golden stars 2007" brochure (EN, with FR, DE, IT, ES, PL language versions available soon).

- Multimedia:

Reproduction of the DVD "Two ways to town-twinning" and insertion of pedagogical questions in the leaflet to the attention of trainers, teachers, etc.

Foreseen: creation of two DVD to illustrate Actions 2 and 4 of the Programme (available in October 2008); Reproduction of the "Europe for Citizens" video-clip DVD (available in EN only)

- Internet:

Revamping of the Citizenship website, the new version of which will be online beginning of June 2008.

Operating grants were awarded to three designated organisations: Association Jean Monnet, Centre Européen Robert Schuman and EUNET (Maisons de l'Europe) which are mainly dedicated to the promotion and visibility of the EU.

- Contact points in Member States and other countries taking part in the "Europe for Citizens" programme

In the framework of the "Europe for Citizens" programme Committee of January 2007, a first discussion took place on the issue of dissemination of information on the programme in the Member States and other countries taking part in the programme.

During the year 2007 further reflections and preparatory work took place and some Member States designated their structures formally for this function. As of the year 2008 the contact points will be co-financed by the programme under the action 3.

These structures are to be contact points for relevant information multipliers, for potential programme beneficiaries, and for the general public. They should play an intermediary role between these stakeholders and the European Commission. Their main tasks will be to mobilise relevant organisations to promote the programme, to facilitate participation in the programme by the widest array of potential candidates, to ensure wide publicity as regards the programme to the general public, and to provide regular feedback from the field to the European Commission.

3.4.	Action 4 – Active European Remembrance

The Action 4, "Active European Remembrance", is a new action within the "Europe for Citizens" programme which targets non-profit making organisations engaged in keeping alive the memory of the victims of Nazism and Stalinism and in preserving the main sites, memorials, former extermination sites and archives documenting these events.

For the period 2004 and 2006, this action was part of the community action plan for the promotion of the active bodies at the European level in the field of the culture (Line: 15 04 01 02 - DECISION N° 792/2004/CE - Decision of the European Parliament and the Council of 21/04/04). It supported only actions related to Nazism.

The inclusion into the "Europe for Citizens" programme was accompanied by a thematic enlargement to Stalinism. This new thematic scope involves an openness regarding the historical period covered.

A new emphasis has also been placed on the way projects relate to the preservation of the memory of the past. The "Europe for Citizens" programme puts the accent on the active European citizenship aspect and on the debate on the future of the EU.

In 2007, 126 applications were received and 36 projects selected (acceptance rate 28%). In terms of the number of applications, Germany, Italy, Poland, France and Hungary are the most active countries.

The Action 4 was prominent for the very high quality of the applications received, as noted by the expert evaluators, and it was deemed to provide a very good fit with the programme. Thematically the selected projects relate fruitfully to the programme's objectives of "fostering action, debate related to European citizenship and democracy, shared values" and of "bringing Europe closer to its citizens by promoting Europe's values".

# 4. Horizontal issues

4.1.	Structured dialogue with the civil society organisations

Since the consultation phase leading to the Commission's proposal for the current 2Europe for Citizens" programme in spring 2005 the Commission has been in a continuous dialogue with the main stakeholders in the field on the programme implementation and on topical policy issues.

In 2007 this dialogue was continued with a general meeting involving the main stakeholders of the programme (so called "Active European Citizenship Group”), and three specific meetings in the area of action 1. The dialogue became more structured and systematic and informal terms of references on the mandate, composition and working method were prepared for the “Active European Citizenship Group”. In addition to the programme implementation, particularly the issue of the European Year of Intercultural Dialogue was addressed in 2007.

4.2.	Dissemination and exploitation of results

The "Europe for Citizens" programme draws particular attention to the issue of dissemination and exploitation of results (valorisation). The main goal is to strengthen the impact of the programme on the citizens, on civil society and on national and European policies in the area of citizenship. The valorisation strategy initiated in 2007 was threefold:

Each project supported by this Programme should make the necessary efforts for ensuring its valorisation. The aspect of dissemination and exploitation has been integrated in the evaluation criteria of applications in all actions and this issue is verified also during the analysis of the final reports.

Structuring projects consist especially of strengthening of existing European networks and thematic co-operation or establishing measures supporting such networking across Europe. This approach was integrated in all measures in 2007.

At programme level, the exploitation and dissemination strategy includes use of the internet sites, publications as well as the use of external media particularly at the occasion of high visibility events. These events are also of particular importance for bringing the results of the programme on the inter-institutional European agenda.

4.3.	Monitoring and Evaluation

Since the start of the programme implementation in 2007, project monitoring has been effected through monitoring visits carried out by the Executive Agency on the field.

The Commission carried out an exploratory exercise to develop of a system measuring the annual impact of activities supported by the programme. To this aim a survey was done targeting the very first projects of the new programme: the first phase of town twinning citizens' meetings in 2007.

Specifically, the aim was to assess whether the participation in the tow twinning activities have – in accordance with the programme objectives - an impact at the level of participants in terms of feeling more European, feeling more tolerant and feeling greater sense of solidarity.

The key findings are as follows:

Feeling more European:

The survey results provide a clear evidence of an important increase of feeling European as an impact of participating in activities supported by the programme.

Feeling a greater sense of solidarity:

Similarly the results provide evidence of an important increase of feeling a sense of solidarity as an impact of participating in activities supported by the programme.

Feeling more tolerant:

Tolerance appeared to be clearly more complicated phenomena to measure. However, the survey provided evidence of a positive shift in feeling more tolerant as a result of participating in the programme activities

A preliminary conclusion can be drawn that participation in the programme activities – in this case town twinning citizens meetings - has a positive impact on the project beneficiaries in line with the programme objectives. Further evidence is however needed to analyse this in more details and to extend this conclusion to all the actions of the programme.

4.4.	Programme management

The Europe for Citizens programme is centrally managed by the European Commission, mainly through the Executive Agency. The available budget was committed to the level of 99 % in line with the budget presented to the programme committee within the 2007 work plan.

The programme management is particularly demanding due to the nature of the programme: it mobilises through a variety of projects many small organisations from national regional and local level. This requires smooth and simple procedures and easily accessible information on grant award systems. This character of the programme presented also a challenge to the launch of the new programme. However, the passage from the previous to the new programme went rather smoothly without any major difficulties.

The new "implementation design" with the programme guide as a core stone was well received by the beneficiaries. The programme guide, which covers the whole programme period 2007-2013, provides the potential applicants with complete information on the programme objectives, on the characters of the different measures, on the grant procedures and on time-tables. The guide has clearly strengthened the identity and internal coherence of the programme.

The Executive Agency was able to handle the selections, grant decisions and payments without any major delays. Important simplification measures were implemented in 2007: the grant agreements were replaced by grant decisions, the use of flat rate systems was extended to new project categories, the on-line applications were introduced on experimental basis for the town twinning citizens meetings. A horizontal exercise to simplify the applications forms for all programmes was launched. However, the programme management remains vulnerable and cost intensive due to the high work load. Consequently further measures to simplify and structure the programme implementation are already in preparation.

According to Article 9 of the Decision establishing the programme, the Commission is assisted, for the implementation of the programme, by a committee comprising representatives of the Member states and of other participating countries.

In 2007, the committee met three times:

-	In January to adopt its rules of procedures and to give an opinion on the 2007 work programme;

-	In April to deliberate on grants awarded within the categories referred to in the Article 9.2.d;

-	In October to give an opinion on the work programme for the year 2008.

The programme committee has provided an important input in the strategic development of the programme and its implementation. Particularly the establishment of the national information structures for the programme was result of an initiative taken by the Member States within the programme committee.

As of June 2007 the programme committee was also consulted in written procedure under the advisory procedure on all other grant selections that those referred to in the Article 9.2.d of the programme decision. This unforeseen procedure, even if done within the shortened deadlines, caused delays is final grant selections and the publications of the related lists. The Commission has proposed a technical change to the basic act in order to limit the consultation of the programme committee to those selections referred to in the Article 9.2.d of the programme decision.

# 5. Conclusions

The year 2007 was a successful launch of the Europe for Citizens programme. The new programme with more ambitious goals was positively received by potential beneficiaries. The closer involvement of the participating countries through the programme committee has created new dynamism and new opportunities.

The most important features and challenges for the future development are the following:

- the programme implementation will reach its full range in course of the years 2008 and 2009

- to increase the impact of the programme more structuring measures nee to be developed and  the emphasis given to exploitation and dissemination of the results must be further strengthened

- the simplification must go further in order to guarantee easy procedures for the beneficiaries and to limit administrative costs

- support measures will be needed in order to develop the quality of the projects. The Europe for Citizens points in the participating countries will have a key role to play in this respect.

List of annexes

1.	Graphic: Number of selected projects by action 2007

2.	Graphic: Total selected projects by theme 2007

3.	Table: Grants attributed, number of projects, number of participants in 2007 (not including the designated organisations)

4.	Table: Action 1 Town twinning Citizens' meetings - Selected projects and the proportion of multilateral projects by country in 2007

5.	Table: Action 1 Town twinning Citizens' meetings - Selected projects: Involvement of invited towns/Involvement of participants from different countries

6.	List: Action1 Thematic Networking of Twinned Towns – Selected projects and themes in 2007

7.	List: Action 2 Active Civil Society in Europe, Measure 1 – European public policy research organisations - Selected organisations

8.	List: Action 2 Active Civil Society in Europe, Measure 2 – Civil society organisations at European level - Selected organisations

9.	Graphic: Action 2 Active Civil Society in Europe, Measure 3 – Civil Society projects by country in 2007

10.	List: Action 3 Together for Europe – Golden Stars Awards in 2007

11.	List: Action 4 - Active European Remembrance: Selected projects and themes in 2007

Annex 3

Europe for Citizens Programme 2007

Grants attributed, number of projects, number of participants

|  |  |  | Action 1 Active Citizens for Europe |  |  |  | Action 2 Active civil society in Europe |  |  |  |  | Action 4 Active European Remembrance |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Town Twinning citizens' meetings |  |  | Thematic networking of twinned towns | Measure 1+2 Operating grants |  |  | Measure 3 Civil Society Projects |  | Remembrance |  |  |  |  |
| Number of Introduced applications |  |  | 1648 |  |  | 89 | 192 |  |  | 197 |  | 126 |  |  |  |  |
| Number of granted applications |  |  | 903 |  |  | 52 | 25 |  |  | 108 |  | 36 |  |  |  |  |
| Grants attributed (EUR) |  |  | 7.983.738,86 |  |  | 961.923,55 | 2.552.007 |  |  | 3.362.100,66 |  | 1.097.753,70 |  |  |  |  |
| Number of participants |  |  | 668.387 |  |  | 6.042 | Not available |  |  | Not available |  | Not available |  |  |  |  |
| Average funding per project funded (EUR) |  |  | 8.841 € |  |  | 18.499 € | 102.080 € |  |  | 31.131 € |  | 30.493 € |  |  |  |  |
|  | Country | Towns participating as invited towns |  |  |  |  |  |  | Mobility (number of travelling participants )/country |  |  |  |  |  |  |  |
|  | D | 371 |  |  |  |  |  |  | 14.984 |  |  |  |  |  |  |  |
|  | FR | 331 |  |  |  |  |  |  | 15.388 |  |  |  |  |  |  |  |
|  | IT | 199 |  |  |  |  |  |  | 7.398 |  |  |  |  |  |  |  |
|  | PL | 199 |  |  |  |  |  |  | 6.188 |  |  |  |  |  |  |  |
|  | RO | 126 |  |  |  |  |  |  | 3.427 |  |  |  |  |  |  |  |
|  | HU | 117 |  |  |  |  |  |  | 4.280 |  |  |  |  |  |  |  |
|  | UK | 107 |  |  |  |  |  |  | 3.481 |  |  |  |  |  |  |  |
|  | E | 80 |  |  |  |  |  |  | 3.225 |  |  |  |  |  |  |  |
|  | SK | 56 |  |  |  |  |  |  | 2.416 |  |  |  |  |  |  |  |
|  | CZ | 50 |  |  |  |  |  |  | 1.435 |  |  |  |  |  |  |  |
|  | BE | 39 |  |  |  |  |  |  | 1.552 |  |  |  |  |  |  |  |
|  | NL | 28 |  |  |  |  |  |  | 877 |  |  |  |  |  |  |  |
|  | AT | 27 |  |  |  |  |  |  | 933 |  |  |  |  |  |  |  |
|  | LIT | 24 |  |  |  |  |  |  | 580 |  |  |  |  |  |  |  |
|  | SE | 22 |  |  |  |  |  |  | 1.183 |  |  |  |  |  |  |  |
|  | IRL | 21 |  |  |  |  |  |  | 695 |  |  |  |  |  |  |  |
|  | LET | 19 |  |  |  |  |  |  | 365 |  |  |  |  |  |  |  |
|  | FI | 18 |  |  |  |  |  |  | 351 |  |  |  |  |  |  |  |
|  | PT | 17 |  |  |  |  |  |  | 567 |  |  |  |  |  |  |  |
|  | BG | 16 |  |  |  |  |  |  | 447 |  |  |  |  |  |  |  |
|  | EE | 16 |  |  |  |  |  |  | 225 |  |  |  |  |  |  |  |
|  | GR | 15 |  |  |  |  |  |  | 360 |  |  |  |  |  |  |  |
|  | SLO | 13 |  |  |  |  |  |  | 351 |  |  |  |  |  |  |  |
|  | DK | 9 |  |  |  |  |  |  | 242 |  |  |  |  |  |  |  |
|  | MT | 6 |  |  |  |  |  |  | 136 |  |  |  |  |  |  |  |
|  | CY | 3 |  |  |  |  |  |  | 104 |  |  |  |  |  |  |  |
|  | LU | 3 |  |  |  |  |  |  | 36 |  |  |  |  |  |  |  |
|  | Total | 1932 |  |  |  |  |  |  | 71.226 |  |  |  |  |  |  |  |
|  | Project Nr. |  |  | Country | Organism |  |  | Town |  |  | Theme |  |  | Partic.(L: local / I: international) | Grant |  |
|  | 07/0004 |  |  | I | COMUNE DI POSITANO |  |  | POSITANO |  |  | Thematic Conference : Posit.Ive Changes |  |  | 133 (98 L; 35 I) | 26.014,29 |  |
|  | 07/0005 |  |  | LET | VALMIERA CITY COUNCIL |  |  | VALMIERA |  |  | Seminar-workshop theme "Valmiera and Twinning Towns - Towards the Best Practice" |  |  | 48 (30 L; 18 I) | 3.763,62 |  |
|  | 07/0006 |  |  | I | COMUNE DI ACI SANT'ANTONIO |  |  | ACI SANT'ANTONIO |  |  | "Reti locali e reti transnazionali per la cittadinanza europea attiva" |  |  | 90 (50 L; 40 I) | 20.325,30 |  |
|  | 07/0007 |  |  | GR | DIMOS AMAROUSSION |  |  | AMAROUSSION |  |  | Conference theme "FORUM of the european citizens and municipal officers: fighting for q-cities, fighting for a better daily life. " |  |  | 132 (82 L; 50 I) | 22.511,40 |  |
|  | 07/0008 |  |  | I | COMUNITÀ MONTANA "SILANA" |  |  | SPEZZANO PICCOLO |  |  | "MILD - Municipalities' Interaction for Local Development" |  |  | 135 (100 L; 35 I) | 17.531,30 |  |
|  | 07/0009 |  |  | I | COMUNE DI CASTELFORTE |  |  | CASTELFORTE |  |  | Conference theme "Città Insieme ... Idee di sviluppo locale" |  |  | 150 (112 L; 38 I) | 20.599,88 |  |
|  | 07/0010 |  |  | I | COMUNITÁ MONTANA "MONTI AURUNCI" |  |  | SPIGNO SATURNIA |  |  | Conference theme "RES - Reti per lo Sviluppo" |  |  | 150 (112 L; 38 I) | 20.599,88 |  |
|  | 07/0011 |  |  | CZ | MESTO PISEK |  |  | PISEK |  |  | "West-und Osteuropa - die Zukunft der Partnerschaften. Die Qualifizierung von Mitarbeitern/-Innen in der Partnerschaftsarbeit" |  |  | 60 (20 L; 40 I) | 9.732,00 |  |
|  | 07/0013 |  |  | A | GEMEINDE MELLACH |  |  | MELLACH |  |  | "Biomasse-Einsatz für Nahwärmenetze auf Gemeindeebene" |  |  | 133 (85 L; 48 I) | 17.928,90 |  |
|  | 07/0014 |  |  | I | MUNICIPALITY OF MONTEBELLUNA |  |  | MONTEBELLUNA |  |  | "Twinning networking as mobility's opportunity" |  |  | 200 (140 L; 60 I) | 26.449,60 |  |
|  | 07/0017 |  |  | I | COMUNE DI POLESELLA |  |  | POLESELLA |  |  | "The women's presence on the Institutions and European Union actions : the town-twinning as an opportunity for network and projects to share" |  |  | 67 (40 L; 27 I) | 10.710,26 |  |
|  | 07/0021 |  |  | H | MORAHALOM VAROS ONKORMANYZATA |  |  | MORAHALOM |  |  | Interkulturális párbeszéd : a kulturális sokszinüség iránti tisztelet, az esélyegyenlöség biztositása a demokratikus kulturális politika keretei között |  |  | 130 (95 L; 35 I) | 16.998,45 |  |
|  | 07/0022 |  |  | F | ASSOCIATION ILLE ET VILAINE POLOGNE |  |  | RENNES |  |  | " Tous citoyens Européens dans l'Europe Elargie" "La Pologne et la Roumanie, deux nouveaux états de l'Europe états de l'Europe des 27 à découvrir" |  |  | 200 (100 L; 100 I) | 28.472,00 |  |
|  | 07/0023 |  |  | H | KISKUNMAJSA VAROS ONKORMANYZATA |  |  | KISKUNMAJSA |  |  | "Gemeinsam für unsere Zukunft" |  |  | 120 (70 L; 50 I) | 16.850,70 |  |
|  | 07/0030 |  |  | I | COMUNE DI PRECI |  |  | PRECI |  |  | "Cittadinanza Attiva Europea : il ruolo delle Città" |  |  | 120 (90 L; 30 I) | 23.788,80 |  |
|  | 07/0032 |  |  | BG | VELIKO TURNOVO MUNICIPALITY |  |  | VELIKO TURNOVO |  |  | "Cultural diversity of the nations for a stronger Europe" |  |  | 100 (70 L; 30 I) | 6.651,00 |  |
|  | 07/0033 |  |  | I | COMUNE DI SAN MINIATO |  |  | SAN MINIATO |  |  | Conference on "Town Twinning and International cooperation actions and projects as rising factor of local communities, with particular reference to young people and students" |  |  | 65 (35 L; 30 I) | 13.015,65 |  |
|  | 07/0034 |  |  | F | ASSOCIATION DES PETITES VILLES DE FRANCE |  |  | PARIS |  |  | "Première rencontre européenne des petites villes jumelées" |  |  | 200 (104 L; 96 I) | 28.252,48 |  |
|  | 07/0035 |  |  | SK | MESTO KOSICE |  |  | KOSICE |  |  | European Cultural Arena |  |  | 116 (20 L; 96 I) | 11.523,36 |  |
|  | 07/0037 |  |  | EE | TARTU CITY GOVERNMENT |  |  | TARTU |  |  | A total Makeover - is it necessary? |  |  | 95 (71 L; 24 I) | 13.038,75 |  |
|  | 07/0039 |  |  | UK | DOWNPATRICK/LISTOWEL LINKAGE GROUP |  |  | DOWNPATRICK |  |  | Youth in Europe through Town Twinning |  |  | 130 (50 L; 80 I) | 29.439,00 |  |
|  | 07/0041 |  |  | D | BERLIN-BRANDENBURGISCHE AUSLANDSGESELLSCHAFT E.V |  |  | POTSDAM |  |  | Kommunale und bürgerschaftliche Strategien für Toleranz und Demokratie |  |  | 105 (56 L; 49 I) | 20.970,96 |  |
|  | 07/0042 |  |  | F | COMITE DE JUMELAGE DE LA VILLE DE PLERIN |  |  | PLERIN CEDEX |  |  | Le developpement durable enjeu pour les citoyens europeens |  |  | 130 (70 L; 60 I) | 28.923,60 |  |
|  | 07/0043 |  |  | D | STADT KARLSRUHE |  |  | KARLSRUHE |  |  | Karlsruhe Städtepartnerschaftstage "Gemeinsam erkennen und vernetzen" |  |  | 40 (20 L; 20 I) | 7.677,00 |  |
|  | 07/0046 |  |  | GR | MUNICIPALITY OF ALEXANDROUPOLIS |  |  | ALEXANDROUPOLIS |  |  | "Environmental impact of large scale infrastructures" |  |  | 114 (70 L; 44 I) | 20.106,06 |  |
|  | 07/0051 |  |  | SLO | MUNICIPALITY OF ZALEC |  |  | ZALEC |  |  | "The Generation Symbiosis" |  |  | 76 (57 L; 19 I) | 14.001,33 |  |
|  | 07/0052 |  |  | LIT | ZARASU RAJONO SAVIVALDYBES ADMINISTRACIJA |  |  | ZARASAI |  |  | Developing culture sector networks in the regions of European Union, while seeking culture dialogue and equal opportunities for european citizenship. |  |  | 105 (75 L; 30 I) | 13.202,10 |  |
|  | 07/0056 |  |  | I | COMUNE DI PADENGHE SUL GARDA |  |  | PADENGHE SUL GARDA |  |  | Reti Internazionali e Cittadinanza Europea Attiva |  |  | 133 (80 L; 53 I) | 27.411,81 |  |
|  | 07/0057 |  |  | PL | URZAD MIEJSKI GNIEZNO |  |  | GNIEZNO |  |  | Implementation of Union funds - reciprocal exchange of experience - conference of twinned towns in Gniezno. |  |  | 90 (60 L; 30 I) | 6.370,20 |  |
|  | 07/0058 |  |  | I | CITTA DI FIUMICINO |  |  | FIUMICINO |  |  | Living in Europe |  |  | 160 (90 L; 70 I) | 23.198,40 |  |
|  | 07/0059 |  |  | FI | MUNICIPALITY OF HAUKIPUDAS |  |  | HAUKIPUDAS |  |  | European juvenile policies structuring the future. |  |  | 133 (99 L; 34 I) | 28.193,13 |  |
|  | 07/0060 |  |  | GR | MUNICIPALITY OF PTOLEMAIDA |  |  | PTOLEMAIDA |  |  | Promoting Participatory Democracy |  |  | 400 (300 L; 100 I) | 21.628,00 |  |
|  | 07/0061 |  |  | S | STORUMANS KOMMUN |  |  | STORUMAN |  |  | Developing a European Identity - The Periphery at the Edge of Development |  |  | 100 (75 L; 25 I) | 22.440,00 |  |
|  | 07/0065 |  |  | F | MAIRIE DE BREST |  |  | BREST CEDEX 2 |  |  | Echanger avec les villes jumelles de Brest autour du Developpement Durable. |  |  | 125 (75 L; 50 I) | 18.234,00 |  |
|  | 07/0066 |  |  | LET | REGION DOBELE |  |  | DOBELE |  |  | Gestern, Heute und Morgen des Kulturtourismus |  |  | 70 (30 L; 40 I) | 7.479,90 |  |
|  | 07/0067 |  |  | F | COMITE DES JUMELAGES D'ANGOULEME |  |  | ANGOULEME |  |  | Rencontre multinationale et citoyenne des Jumelages angoumoisins |  |  | 75 (55 L; 20 I) | 15.887,40 |  |
|  | 07/0069 |  |  | UK | COUNTY COUNCIL OF THE CITY AND COUNTY OF CARDIFF |  |  | CARDIFF |  |  | Generation Europe |  |  | 120 (90 L; 30 I) | 17.614,20 |  |
|  | 07/0070 |  |  | I | ASSOCIAZIONE NATIONALE COMUNI DEL LAZIO |  |  | ROME |  |  | IDEA - Intercultural dialogue exchanges activities |  |  | 133 (50 L; 83 I) | 26.387,61 |  |
|  | 07/0073 |  |  | UK | ABINGDON TOWN COUNCIL |  |  | ABINGDON |  |  | Equal Opportunities for all in the European Year of Equality , 2007 |  |  | 28 (8 L; 20 I) | 10.761,96 |  |
|  | 07/0075 |  |  | D | STADT BAMBERG |  |  | BAMBERG |  |  | Fachtagung Internationale Partnerschaft |  |  | 60 (30 L; 30 I) | 13.015,50 |  |
|  | 07/0076 |  |  | D | LANDKREIS PEINE |  |  | PEINE |  |  | Bildungskonferenz der Europaischen Partner des Landkreises Peine |  |  | 79 (30 L; 49 I) | 15.947,82 |  |
|  | 07/0078 |  |  | DK | MUNICIPALITY OF VIBORG |  |  | VIBORG |  |  | Active twinning - a tool for developing the inclusive school |  |  | 130 (70 L; 60 I) | 32.404,20 |  |
|  | 07/0080 |  |  | S | CITY OF SMEDJEBACKEN |  |  | SMEDJEBACKEN |  |  | Networking for a longterm cooperation on important themes in Europe / City of Smedjebacken |  |  | 132 (132 I) | 32.362,56 |  |
|  | 07/0082 |  |  | I | COMUNE DI MACERATA |  |  | MACERATA |  |  | Twinned towns: A Bridge from Past to Future |  |  | 63 (45 L; 18 I) | 13.301,31 |  |
|  | 07/0084 |  |  | D | STADT ISERLOHN |  |  | ISERLOHN |  |  | Von der Völkerverstandigung zur Projektarbeit - Internationale Zusammenarbeit der Kommunen in Netzwerken |  |  | 107 (27 L; 80 I) | 25.727,79 |  |
|  | 07/0085 |  |  | F | ASSOCIATION CASTEL |  |  | ST. PIERRE D'OLERON |  |  | Conference: "Bulgarie, Roumanie, nouveaux entrants" Ateliers: " Jeunesse et mobilite europeenne" |  |  | 240 (120 L; 120 I) | 18.283,20 |  |
|  | 07/0086 |  |  | I | ASSOCIAZIONE NATIONALE COMUNI DEL LAZIO |  |  | ROME |  |  | ROSE-Re-qualification of sustainable Eco-tourism |  |  | 132 (50 L; 82 I) | 20.406,24 |  |
|  | 07/0087 |  |  | P | JUNTA DE FREGUESIA DO ESTORIL |  |  | ESTORIL |  |  | Networking in the comunity - a pathway for inclusion |  |  | 130 (50 L; 80 I) | 20.061,00 |  |
|  | 07/0088 |  |  | I | COMUNE DI FONTANELLATO |  |  | FONTANELLATO |  |  | Keys for Innovative Education |  |  | 128 (80 L; 48 I) | 24.583,20 |  |
|  | 07/0093 |  |  | UK | NEWCASTLE CITY COUNCIL |  |  | NEWCASTLE UPON TYNE |  |  | Exploring European Identity through Intercultural Dialogue: Challenging the stereotype of migrants |  |  | 70 (40 L; 30 I) | 16.890,30 |  |
|  | 07/0094 |  |  | D | GEMEINDE HUDE |  |  | HUDE |  |  | Die Rolle der EU in der kommunalen Arbeit |  |  | 35 (10 L; 25 I) | 8.837,70 |  |
|  | 07/0095 |  |  | D | STADT AACHEN |  |  | AACHEN |  |  | Europa ist hier! Europaeische Kurs fur Deutschlehrer - /innen aus den Partnerstadten Aachens |  |  | 25 (5 L; 20 I) | 5.418,45 |  |
|  | 52 projets |  |  |  |  |  |  |  |  |  |  |  |  |  | 961.923,55 |  |

Annex 7

Europe for Citizens Programme Action 2 – Active Civil Society in Europe Measure 1 - European public policy research organisations (think tanks) List of selected organisations

- Centre for Economic Policy Research

- Friends of Europe

- European Policy Centre

- Centro Europa Scuola Educazione e Società (CESES)

- Europäiche Akademie Berlin e.V. (EAB)

- European Citizen Action Service (ECAS)

- Centre for European Policy Studies (CEPS)

- Trans European Policy Studies Association (TEPSA)

- The Lisbon Council for Economic Competitiveness and Social Renewal

- Confrontations Europe

- Institute of European Affairs (IEA)

Annex 8

Europe for Citizens Programme Action 2 – Active Civil Society in Europe Measure 2 - Civil society organisations at European level List of selected organisations

- Centre Européen Juif d'Information (CEJI)

- SOLIDAR

- European Volunteer Center (CEV)

- Assembly of European Regions (AER)

- Union of European Federalists (UEF)

- European Council for Non Profit Organisations (CEDAG)

- Netzwerk Migration in Europa

- Europa Jovoje Egyesulet (Futur of Europe Accosiation)

- The Association of Service Civil International in Europe

- Heinrich-Böll-Stiftung e.V.

- Utonomia Foundation

- The Intercultural Communication & Leadership School (ICLS)

- Confédération des Organisations Familiales de l'Union européenne (COFACE)

- European Trade Union Committee for Education (ETUCE)-Comité Syndical Européen pour l'Education (CSEE)

Annex 10

Europe for Citizens Programme Action 3 – Together for Europe The "Europe for Citizens" Forum 2007 and Golden Stars Awards "Golden Stars" attribution 2007

Town-twinning projects:

- Nether Kellet (UK): Conservation of energy and natural resources

- Le Coudray St Germer (FR): "Enfants du pays, parents de l'Europe" une même citoyenneté malgré la diversité des origines

- Tekovske Luzany (SK): Citizens Together - Without Borders

- Hennef (DE): Europe Week

- Wągrowiec (PL): The days of Europe 2006 - Solidarity in Europe, hundreds of ideas, thousands of friendship"

Civil Society Projects:

- Netzwerk Migration Europa (DE): European Forum - Learning In Immigration Societies: For Human Rights Oriented Democracy in Europe

- Centrum pro komunitni praci stredni Morava (CZ): How to become an active European citizen?

- Hellenic Foundation for European and Foreign Policy (GR): Communicating EU Values across Greece

- Europahuset Gävleborg (SE): The Baltic adventure! Youth travelling on the roads of enlargement

- United Religions Initiative Europe AISBL (DE): Overcoming irritations and prejudices between people of different cultures, religions and convictions in the EU enlargement process"

Special recognition:

The jury that selected this year's Golden Star winners found two projects not selected for Golden Star nevertheless deserved recognition

- Town twinning project:
Municipality of Dobrich, Bulgaria: A good example of engaging in thematic cooperation through town twinning, through a variety of projects and events around renewable and alternative energy, agriculture and sustainability

- Civil society project
General Workers' Union, Malta: A project exploring the role of trade unions in EU policy making, forging national and transnational links with other civil society actors, in Malta and the UK. The project produced a toolkit to be disseminated for continued use in the future.

Some projects focus on several themes

Not including the designated organisations

Figure indicated in the grant applications