|  | EUROPEAN COMMISSION Directorate-General for Education and Culture Youth, sport and citizenship Citizenship policy: "Europe for Citizens" |
| --- | --- |

EFCC/120/2009-EN

Brussels, 2 June 2009

EAC D4/

Report on the activities under the "Europe for Citizens" programme 2008

# 1. Introduction

The aim of this document is to provide an overview of the progress made in implementing the “Europe for Citizens" programme in 2008. The report outlines activities carried out in line with the 2008 work programme, on which the programme committee had delivered a favourable opinion on 23 October 2007.

2008, the second year of implementation of the new programme, was marked by a full rolling out of all measures not launched in 2007 owing to budgetary reasons (studies) or phased programming reasons (citizen’s projects, support measures). Measures established in 2007 were also consolidated and, in some cases, strengthened (town twinning networking).

Particular attention was given to reinforcing visibility through the creation of Europe for citizen’s contact points in the majority of participating countries, the organisation of a major event under the French Presidency and the launching of a new Citizenship web site at European level. Efforts to improve evaluation were continued through the launching of a follow-up study aimed at better measurement of the qualitative effects of the programme.

# 2. Political context and priorities

Consultation with stakeholders in the lead-up to the design of the 2007-2013 programme indicated that a combination of permanent and annual priorities was necessary to provide both a stable strategic framework to steer the implementation of the programme and a degree of flexibility to respond to issues as they arise.

The permanent priorities guide and encourage the beneficiaries to work on a longer-term basis on aspects directly linked to the objectives of the programme. This creates a critical mass of activities around the core issues of the programme and facilitates thematic networking between the beneficiaries. Whilst the annual priorities are used to mobilise the beneficiaries to address the most topical European issues and new initiatives related to the permanent priorities.

The priorities are:

- The future of the European Union and its basic values (with a specific focus in 2008 on new institutional developments & celebrations of Europe day);

- Active European citizenship: participation and democracy in Europe (with a specific focus in 2008 on women’s participation in political life as part of the follow-up to the 2007 European Year – ‘ Equal opportunities for all);

- Intercultural dialogue (with a specific focus on the 2008 European Year of ‘Intercultural dialogue’);

- People's well being in Europe: employment, social cohesion and sustainable   development (with a specific focus in 2008 on sport for active citizenship and social inclusion in line with the 2007 White Paper);

- The impact of EU policies in societies with a specific focus in 2008 on creativity and innovation in line with the 2009 European Year).

The debate surrounding the Lisbon Treaty and the future of the EU institutions combined with the preparations for the European Parliament elections, underlined the growing importance of the active involvement of citizens in the construction of Europe and ensured that the issues dealt with in the Europe for Citizens programme were high on the political agenda in 2008. Key beneficiaries of the Europe for Citizens programme took part in Plan D and Debate in Europe events aimed at strengthening dialogue and democracy in Europe.

# 3. Implementation of the "europe for Citizens" Programme

In 2008, the momentum developed through the launch of the new programme in 2007 was maintained, progress was consolidated and some aspects of the programme were further developed. The scale and reach of the programme continued to grow. Over 1,500 projects were selected/grants awarded and over a million participants were expected to be involved in the co-financed activities. Just over 23 million Euros was committed.

Although some aspects of the programme are very difficult to measure, a sample survey of Town-Twinning meetings indicated that participation in these kinds of activities contributes strongly to increased knowledge on the EU, a greater sense of feeling European and of solidarity.

The structured dialogue continued to develop with four meetings held in 2008, involving a broad range of representatives of European and international civil society organisations. This dialogue not only encourages broader debate on active European citizenship issues but supports networking/exchange of practice and promotes the visibility of the programme.

In 2008, most actions of the programme were implemented through the general calls for proposals linked to the programme guide. Two specific calls for proposals were carried out – one for citizens’ projects and support measures under Action 1.4 and one for structural support for European level think-tanks and civil society organisations.

Thematically, the focus concentrated on the following issues:

-	Intercultural dialogue (926 selected projects);

-	Active European Citizenship, participation and democracy (458 selected projects);

-	Equal opportunities (261 selected projects);

-	Social inclusion (246 selected projects);

-	Employment (235 selected projects)

-	Future of the European Union (204 selected projects).

This demonstrates that the priorities are broadly successful in mobilising participants and creating a critical mass of activities around the most relevant topical issues.

3.1.	Action 1 – Active Citizens for Europe

Action 1 consists of three sub-measures: "Town twinning Citizens' meetings", "Thematic networking of twinned towns" and, newly introduced in 2008, ''Citizen’s Projects and support measures''. Under this action, Structural assistance is also provided for the Council of European Municipalities and Regions (CEMR) as a designated organisation.

In 2008, the networking of twinned towns was strengthened through the introduction of a multiannual option which enables towns to develop a variety of activities and is aimed at improving the sustainability and visibility of the co-financed events. This, together with the policy to encourage more multilateral events, has helped broaden the geographic outreach of the activities supported and opened up opportunities to involve more towns. The number of municipalities benefiting rose by over 800. In 2008, 3630 towns were involved in town twinning projects compared to 2828 in 2007.

2008 also saw the launch of citizen’s projects and support measures with activities getting underway at the end of 2008/beginning of 2009.

- Town twinning Citizens meetings

Town twinning citizens’ meetings consist in bringing together a wide range of citizens and citizens’ groups from twinned towns, taking benefit of the partnership between the municipalities for developing strong, informal and personal relations between their citizens. The meetings combine an informal character emphasizing the "learning by doing" approach with a thematic focus in line with the programme priorities.

This measure involves many projects and participants, and its impact comes partly through the volume of direct participation of citizens. In 2008, 1.758 applications were introduced (an increase of around 150 compared to 2007) and 1.111 selected (an acceptance rate of 63% compared to 55% in 2007).

Data presented by the selected beneficiaries show that around 75.000 citizens were expected to move across Europe to participate in a town twinning meeting in another country. When participation at local level is added to the ‘mobile’ participants, the number of citizens involved altogether rises to over 900.000. In this way the programme meets the objective of "bringing together people from local communities across Europe to share and exchange experience, opinions and values".

France, Germany, Italy, Hungary and Poland are the most active countries in hosting citizens meetings. However, the geographic impact goes beyond the host country since every project involves citizens from invited town(s) from other country/countries. Emphasis has been put on encouraging multilateral citizens meetings and the figures show a gradual positive trend. In 2008, 49% of the town twinning citizens meetings were multilateral, (involving at least 3 towns from 3 different countries) compared to 46% in 2007 and 40 % in 2006.

- Thematic networking of twinned towns

A large number of municipalities in Europe are twinned to other towns, which may, in turn, themselves be twinned to further towns. This measure aims at using the potential of the networks created through a series of town twinning links to develop thematic cooperation. Such co-operation enables the participating towns to develop, structure, and strengthen the strategic dimension of town twinning.

At the level of the Community programme, thematic networking is a structuring measure, which extends the dimension of town twinning from people to people meetings to more focussed discussions and systematic exchange of good practice.

96 applications were submitted - a slight increase compared to 2007, but still rather low. 68 were selected resulting in an acceptance rate of 71%. Take-up of the option for multi-annual projects for established networks of twinned towns was also limited. 10 applications were submitted of which 9 were selected - an acceptance rate of 90%.

Implementing the networking measure to its full potential will take time and more awareness-raising efforts to mobilise possible beneficiaries. To support these efforts it was decided that, from 2009, reforms would be introduced to make the networking measure both more flexible and more accessible.

  - Citizen’s Projects and support measures

A new measure aimed at promoting innovative approaches to active participation was introduced in 2008. It supports a variety of transnational and cross sectoral projects directly involving citizens with the intention of feeding their views into the policy process at European level. Drawing on the lessons learned from the pilot citizens’ panels run in 2007, it was decided to structure the projects around specific policy themes of European relevance to ensure more focused debate.

There was a good level of interest in this new measure and a total of 45 applications were received from a broad range of organisations including: municipalities; regional groupings and universities, as well as a large number of NGOs. 18 citizen panel proposals were selected involving 24 Member States and Croatia. In terms of thematic focus, 9 of the panels will concentrate on intercultural dialogue, 4 on institutional development, 3 on sport and 2 on women’s participation. A working group involving representatives from the DG EAC Units responsible for culture, youth and sport in addition to citizenship, has been set up to follow the work of the panels and take account of the ensuing citizens’ recommendations.

New support measures aimed at revitalising town twinning activities and developing longer-lasting partnerships and networks were also introduced in 2008. These measures should enhance the quality of town-twinning activities through reinforcing thematic co-operation and building capacity. Intermediary organisations, such as associations and federations of local authorities, with specific knowledge will share their expertise and good practice with towns with less twinning experience. 18 applications were received, of which 16 were selected – an acceptance rate of 88%. Nearly 40% of the selected projects came from one of the Member States acceding in 2004 or later. In addition to networks and associations of municipal and regional authorities, successful applicants include thematic networks working in the social and democratic field.

- Structural support for and dialogue with CEMR

The Council of European Municipalities and Regions – an organisation designated for an operating grant by the Europe for Citizens programme’s basic act – has a privileged position in terms of representing the town twinning movement to the European Commission. The Commission holds a regular dialogue with the CEMR to get feedback from the field and to exchange views concerning future development. In 2008, the CEMR provided a valuable resource to facilitate town twinning by designing a new web-page including a modern on-line partner search tool and information on global town twinning possibilities. A particular effort was made to raise awareness of opportunities to engage in twinning relations with developing countries.

3.2.	Action 2 – Active Civil Society in Europe

This action is aimed at fostering debate and reflection related to European citizenship and democracy, shared values, common history and culture through cooperation amongst civil society organisations at European level. The action consists of three measures, two of which provide operating grants, respectively to European level think tanks and civil society organisations, and one of which provides grants to civil society projects. A particular focus of activity in 2008 across the three measures was preparatory activities related to the European Parliament elections.

To reinforce co-operation, provide greater continuity and simplify procedures, two important changes were made in 2008 to the structural support measures: the introduction of multi-annual partnerships and the optional use of flat rates and lump sums. These new possibilities have been welcomed by applicants. The vast majority have adopted a multi-annual approach and there has been a good take-up of flat-rate and lump sum options. There was a decrease in the number of organisations applying for the two structural support measures – around 130 compared to almost 200 in 2007 whilst there was an increase of almost a hundred applications for the projects measure. These shifts clearly reflect a growing understanding on the part of the applicants of the kind of profile and activities best suited to the different measures.

In 2008, it was decided to switch the budget surfeit from the projects measure to the structural support measures in view of the strong relevance of the proposed activities to the programme’s objectives and of the higher quality standard of the applications.

  - Structural support for European public policy research organisations (think tanks)

This measure is aimed at strengthening the institutional capacity of European think tanks, which are able to provide new ideas and reflections on European issues, on active European citizenship or on European values. The intention is to promote wider contacts across Europe, and focus attention on key concepts in the area of active European citizenship, in particular the role and functioning of the European democratic structure and citizens' participation

In 2008, in addition to the organisations designated in the basic act (Notre Europe and Institut für Europäische Politik) operating grants were awarded to 11 organisations. Of these 11, 10 received support via a multi-annual partnership and 1 via an annual grant. Three new organisations were supported in 2008. This represents a reasonable balance between continuity and openness to newcomers, thus developing and strengthening partnerships while giving access to new organisations.

- Structural support for civil society organisations at European level

This measure provides civil society organisations of European dimension with better capacity and stability to develop their activities at European level. The purpose is to contribute to the emergence of a structured and active civil society at European level. A wide range of themes and activities are covered but one common feature is work on methodologies to boost citizens' participation in the European context.

In 2008, since many applications of high quality were received the budget for this measure was significantly increased to enable support to be provided to a larger number of organisations. In addition to the three organisations designated in the basic act: the Social Platform, the European International Movement and the European Council on Refugees and Exiles (ECRE), operating grants were awarded to 28 civil society organisations at European level (19 via a multi-annual partnership and 9 via annual grants). This is more than twice as many as in 2007, when operating grants were awarded to 14 non-designated organisations.

The increase in the budget opened the door to many organisations which had not previously received an operating grant - over 60% of the selected applicants were newcomers.

- Support for projects initiated by civil society organisations

The aim of this measure is to support cooperation on concrete projects of civil society organisations from different participating countries. This helps foster mutual understanding of diverse cultures and the identification of common values. To develop capacity and reach wider audiences, activities should have a strong European dimension and thematic focus.

In 2008, there was a significant rise in the number of applications submitted for this measure – almost 300 compared to less than 200 in 2007. Consequently the chance of being selected went down from 55% in 2007 to 46%. 131 projects were selected from a variety of organisations, at local, regional and national level as well as European. The countries with the largest number of selected projects were Hungary, Germany, France, Belgium and Italy. The proportion of selected projects from the Member States which acceded to the EU in 2004 is continuing to rise, reaching 37% compared to 34% in 2007 and 19% in 2006.

As in 2007, many of the projects concerned trans-national seminars and conferences initiating reflection and debate on European issues. The challenge continues to be how to capitalise and follow-up on these events and improve communication and dissemination of results so they become part of a longer-term process.

3.3.	Action 3 – Together for Europe

In 2008, special attention was paid to the launching of the Presidency events, preparatory assessment of the programme in view of the forthcoming interim evaluation and a Europe-wide study on volunteering.

- High visibility events

In 2008, two high visibility events took place.

The Presidency event in La Rochelle, France "European Civic Days":

For the first time, in September 2008, in partnership with the French Presidency an EU Presidency event was co-funded by the Europe for Citizens programme. This marked an important step in raising the profile and political awareness of the programme. The event consisted of three European civic days pioneering a new type of broad participation approach and focusing on issues of mobility, participation and dialogue and their consequences for the European and local context. Attendance was high with close to one thousand representatives from a wide range of interested parties, including associations and non-governmental organisations, officials from local, regional, national and European institutions as well as specialists on European citizenship. Key civic participation issues identified for future development included civil society mentoring and the question of the legal status of associations at European level. The event raised a lot of media interest and publicity. 60% of the funding (€ 250.000) was provided by the programme.

The "Europe for Citizens" Forum 2008 and Golden Stars Awards:

The Europe for Citizens forum was organised in December 2008 in Brussels under the title: "Participation for making a difference". The presence of approximately 500 participants, the strong interest that participants demonstrated for the theme as well as the very active interaction between participants and speakers confirmed the choice to build this annual event around topical themes. The award ceremony was held separately from the main conference at Concert Noble. The exhibition on the 10 Golden Stars projects, the award ceremony and the conference organised on the second day offered numerous possibilities for networking. 27 journalists of 11 nationalities attended and reported back on the event in their countries.

The main conclusion arising from the event was the need for civic participation to be recognized as a subject in its own right. Emphasis was put on the fact that civic participation confers vitality and legitimacy to the European democratic system as well as helping to promote a common European identity. Mobility was seen as one of the most effective tools to promote civic participation in the EU context. It was noted that strengthening participatory democracy means strengthening representative democracy. The importance of the Europe for Citizens Programme being complemented by a relevant accompanying policy was underlined.

Future Presidency events:

Contacts were taken with the Czech Presidency to organise an event in the first half of 2009. To mark the twenty year anniversary, it was agreed that the topic would be the fall of the iron curtain. All the preparatory and contractual aspects were concluded before the end of 2008. The Europe for Citizens programme provided a 60% co-funding (€250.000) to the event.

- Information and dissemination tools

Building on the broad range of promotional and information material developed in 2007 at the launch of the new programme, the following were produced and widely disseminated during the course of 2008:

- Publications:

A brochure on the 2008 Golden Stars awards showcasing the twelve winning projects under the town twinning, civil society and remembrance actions. The brochure exists in EN/FR/DE/IT/ES/PL and is available electronically via the internet site as well as in hard-copy.

- Multimedia:

Two DVDs were produced illustrating projects selected under action 2 – Active civil society in Europe and action 4 – Active European Remembrance. These are both available in all Community languages.

- Internet:

A new more user-friendly and attractive Citizenship website went online in 2008.

Operating grants continued to be awarded to the three designated organisations: Association Jean Monnet, Centre Européen Robert Schuman and EUNET (Maisons de l'Europe) for their activities dedicated to the promotion and visibility of the EU.

- Contact points in Member States and other countries taking part in the "Europe for Citizens" programme

Following an initiative proposed by the programme committee, Europe for Citizens Contact points have been established in 23 countries. These are intended to be decentralised communication structures acting as contact points for information multipliers, for potential programme beneficiaries and for the general public. They are expected to play an intermediary role between these stakeholders and the European Commission. The co-ordinating bodies were designated by the Member States. 17 of these structures applied for, and were awarded co-financing to help cover the operating costs of new information and liaison activities to be undertaken. Representatives of the Contact Points participated in the main high visibility events including the November Forum and the Golden Stars Award Ceremony and a programme of meetings and training to equip them to play their role began to be implemented in 2008.

- Studies

A call for tender for a comparative study on volunteering in the European Union was launched in the second half of 2008. The study will provide an overview of volunteering across the EU, analyse key common issues, trends and challenges and provide recommendations. It will be a useful input to reflection on the preparation of the European Year of Volunteering in 2011. GHK consultancy was selected at the end of 2008 and the results of the study are expected for the end of 2009. The budget is € 300.000.

Studies concerned with the evaluation of the programme are reported on under section 4.3 ‘Monitoring and Evaluation’.

3.4.	Action 4 – Active European Remembrance

This measure targets non-profit making organisations engaged in keeping alive the memory of the victims of Nazism and Stalinism and in preserving the main sites, memorials, former extermination sites and archives documenting these events. This awareness of our past will also feed in to reflection on the origins of the EU and its future. Financing was simplified in 2008 by the introduction of flat-rates.

In 2008, 131 applications were received of which 49 were selected – an acceptance rate of 37% compared to 28% in 2007. The external evaluators considered the projects to be of very high quality and especially relevant to the overall objectives of the programme of "fostering action, debate related to European citizenship and democracy, shared values, common history and culture" and of "bringing Europe closer to its citizens by promoting Europe's values and achievements”.

The countries with the highest number of selected projects were: Germany, Austria, France, Poland and Italy.

# 4. Horizontal issues

4.1.	Structured dialogue with the civil society organisations

In addition to the Forum, which provides an opportunity for debate with a very broad range of stakeholders, the more systematic dialogue established in 2007 (the so called "Active European Citizenship Group) was further developed in 2008. In 2008, 3 meetings of the core group involving around 50 European or international level organisations took place. The discussions covered a wide range of issues relating not only to programme implementation but also to broader initiatives (such as the European Year of Creativity and Innovation and the European Transparency Initiative). Particular attention was given to the follow-up of the Year of Intercultural dialogue. A special sub-group was set up for this purpose and had their first meeting at the end of 2008.

4.2.	Dissemination and exploitation of results

To strengthen the impact of the programme on citizens, on civil society and on national and European policies in the area of citizenship, good dissemination and exploitation of results is of crucial importance. 2008 saw the consolidation of the strategy initiated in 2007 with action at three levels:

- individual project level where dissemination and exploitation should be an integral element. This is one of the criteria for evaluation of all applications and is verified in the analysis of their final report;

- structuring projects to strengthen European networks and thematic co-operation. This was further developed in 2008 in particular in town twinning and structured support for European level think tanks and civil society organisations;

- programme level through the use of multimedia as well as the Golden Stars and high visibility events. Clear progress was made in 2008, particularly in the high visibility events and the revamped citizenship web-site.

Overall, despite the progress made, the full potential of dissemination and exploitation of results remains to be developed, especially at the level of individual projects. The new Europe for Citizens' Contact Points should play a key role in the future.

4.3.	Monitoring and Evaluation

Since the start of the programme implementation in 2007, project monitoring has been effected through monitoring visits carried out by the Executive Agency. 22 such visits took place in 2008. The sample of projects visited is decided upon taking account of geographical spread, coverage of all the actions in the programme and the size of grant awarded.

Building on the study undertaken in 2007 aimed at developing indicators and measuring the effects of participation in town twinning citizens meetings, in 2008, the Commission launched a follow-up study to fine-tune the indicators and extend the measurement of impact to all the actions of the programme. This study is being carried out by ECOTEC via the DG EAC evaluation framework contract. The budget is € 76.000. The results of the study are expected in the autumn of 2009 and will feed into the interim evaluation exercise.

4.4.	Programme management

The Europe for Citizens programme is centrally managed by the European Commission, mainly through the Executive Agency. The available budget was committed to the level of 99% in line with the budget presented to the programme committee within the 2008 work plan.

The "implementation design", introduced in 2007, continued to function well. The programme guide, which covers the whole programme period 2007-2013, provides the potential applicants with complete information on the programme objectives, on the character of the different measures, on the grant procedures and on time-tables. The guide has increased transparency and strengthened the identity and internal coherence of the programme.

Overall in 2008, there was a rise in both the number of applications for the various actions and the number of projects selected /grants awarded. Out of around 2500 applications, a total of almost 1460 were selected, which corresponds to a success ratio of 66% of eligible applications. Despite the bigger volume of work, the Executive Agency was able to handle the selections, grant decisions and payments without major delays.

In 2008, new actions were introduced (support measures, citizens' panels) and important steps were taken to further simplify procedures (multi-annual partnership agreements for operating grants and networking of twinned towns, flat rates for operating grants and modification of the basic act to limit the comitology procedure to large grants from 2009). These steps are important contributions to improving the cost-effectiveness ratio of the programme administration. However, since the programme involves small grants to many organisations it remains demanding to manage.

In line with Article 9 of the Decision establishing the programme, the Commission is assisted, in the implementation of the programme, by a committee comprising representatives of the Member states and participating countries. In 2008, the committee met two times: in March to approve the revision of the 2008 work programme and discuss the results of the evaluation of the 2004-2006 programme and in June to adopt the 2009 work programme and discuss the annual activity report for the 2007. The closer involvement of the participating countries through the programme committee provided an important contribution by ensuring a broader perspective on implementation.

# 5. Conclusions

2008 was a successful period of consolidation and development of the Europe for Citizens programme. Programme implementation reached its full range covering all of the actions and more structuring measures were developed to increase effectiveness and simplifications introduced to improve efficiency. The establishment of the Europe for Citizens Contact points in the vast majority of participating countries has laid the foundations for further improvement of the quality and impact of the projects through better information and communication to potential participants and more systematic and strategic exploitation and dissemination of results.

In the coming period particular attention will be given to: the mid term evaluation of the first three years of the programme; the mobilisation of stakeholders for the European Year of Volunteering in 2011 and reinforcing the learning mobility dimension of the programme.

The key challenge will be to develop stronger links between the programme and policy. The European Year of Volunteering and the forthcoming Green Paper on learning mobility offer good opportunities to raise awareness of the importance of civic participation and to provide input for reflection on the future programme cycle.

List of annexes

- Table: Overview of projects selected/grants awarded by action 2008

- Table: Overview of participants by action 2008

- Graphic: Number of selected projects by action 2008

- Graphic: Total selected projects by theme 2008

- Graphic: Action 1 ‘Town Twinning citizens’ meetings’ – selected projects and the proportion of multilateral projects by country 2008

- a) List: Action 1 ‘Networks of twinned towns’ – selected annual projects 2008

b) List: Action 1 ‘Networks of twinned towns’ – selected multiannual projects 2008

- List: Action 1 ‘Citizens’ projects and support measures’ – selected citizens’ projects 2008

- List: Action 1 ‘Citizens’ projects and support measures’ – selected support measures projects 2008

- List: Action 2 ‘Active civil society in Europe, measure 1 European public policy research organisations’ – selected organisations 2008

- List: ‘Action 2 Active civil society in Europe, measure 2 Civil society organisations at European level’ – selected organisations 2008

- List: ‘Action 2 Active civil society in Europe, measure 3 – Civil society projects - selected projects 2008

- List: Action 3 ‘Together for Europe’ – Golden Stars awards in 2008

- List: Action 3 ‘Together for Europe’ – Europe for Citizens Contact Points established in 2008

- List: Action 4 – ‘Active European Remembrance’ Selected projects 2008

| Actions | Applications received | Non eligible projects | Ineligibility ratio | Selected projects | Success ratio | Grant requested | Grant awarded |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Action 1 |  |  |  |  |  |  |  |
| Town twinning Citizens meetings | 1758 | 222 | 13% | 1111 | 60% | 14.603.459,59 € | 10.234.270,50 € |
| Networks of twinned towns | 96 | 13 | 13% | 68 | 70% | 1.448.971,71 € | 1.096.355,74 € |
| Town twinning multiannual | 10 | 1 | 10% | 9 | 90% | 1.174.443,34 € | 1.109.574,78 € |
| Citizens Projects | 45 | 6 | 13% | 18 | 40% | 4.771.000,00 € | 2.133.224,13 € |
| Support measures | 18 | 1 | 6% | 16 | 88% | 709.726,32 € | 669.726,33 € |
| Action 2 |  |  |  |  |  |  |  |
| Structural support to think tanks and to civil society organisations | 149* | 21 | 14% | 38 | 25% | 12.149.536,20 € | 3.912.932,79 € |
| Financial support to projects initiated by civil society organisations | 287 | 26 | 9% | 131 | 46% | 9.216.856,53 € | 4.079.919,88 € |
| Action 3 |  |  |  |  |  |  |  |
| Information structures | 17 | NA | 0% | 17 | NA | 417.467,64 € | 417.467,64 € |
| Presidency events | NA | NA | NA | 1 | NA | 250.000,00 € | 250.000,00 € |
| Action 4 |  |  |  |  |  |  |  |
| Active European Remembrance | 131 | 19 | 14% | 49 | 37% | 3.955.081,26 € | 1.719.233,18 € |
| Designated organisations |  |  |  |  |  |  |  |
| Designated organisations | NA | NA | NA | 8 | NA | 2.145.000,00 € | 2.145.000,00 * |
| TOTAL | 2362 | 309 | 13% | 1466 | 62% | 50.841.542,59 € | 25.622.704,97 € |
|  | * Covering 129 organisations |  |  |  |  |  | * Excluded the 680.000 euros allocated to the Social Platform by the Budget line 040409 |

Annex 2

Europe for Citizens Programme 2008

Grants attributed, number of projects, number of participants

|  | Action 1 Active Citizens for Europe |  |  |  | Action 2 Active civil society in Europe |  | Action 4 Active European Remembrance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Town Twinning citizens' meetings | Thematic networking of twinned towns | Multi-annual Projects for networks of twinned towns | Support Measures | Measure 1+2 Operating grants | Measure 3 Civil Society Projects | Remembrance |
| Number of Introduced applications | 1.758 | 96 | 10 | 18 | 149 | 287 | 131 |
| Number of granted applications | 1.111 | 68 | 9 | 16 | 38 | 131 | 49 |
| Grants attributed (EUR) | 10.234.270,5 | 1.096.355,74 | 1.109.574,78 | 669.726,33 | 3.912.932,79 | 4.079.919,88 | 1.719.233,18 |
| Number of participants | 984.567 | 9.453 | 44.457 | 41.291 | Not available | Not available | Not available |
| Average funding per project funded (EUR) | 9.211,7 | 16.122,8 | 123.286,08 | 41.857,8 | 102.971,9 | 31.144,4 | 35.086,3 |

| Networks of twinned towns 2008 |  |  |  |
| --- | --- | --- | --- |
| FILE | Country | Organisation name | Grant request |
| 08/0066 | A | Stadtgemeinde Schladming | 17.020,50 € |
| 08/0006 | AT | STADTGEMEINDE BRUCK AN DER MUR | 22.413,00 € |
| 08/0080 | CZ | Town of Novy Bydzov | 17.424,48 € |
| 08/0028 | CZ | VYSOCINA REGION | 18.230,00 € |
| 08/0083 | D | Stadt Leverkusen | 17.529,45 € |
| 08/0063 | D | Gemeinde Sekach | 26.031,00 € |
| 08/0095 | D | Bezirk Mittelfranken | 12.177,00 € |
| 08/0011 | D | Stadtverwaltung Bottrop | 6.618,00 € |
| 08/0081 | D | Gemeinde Neuenkirchen | 5.338,50 € |
| 08/0061 | D | Hochsauerlandkreis | 23.438,85 € |
| 08/0064 | D | Tourist Information Stadt Teltow | 24.972,00 € |
| 08/0046 | D | Gemeinde Eslohe (Sauerland) | 8.409,30 € |
| 08/0086 | D | Stadtverwaltung Warendorf | 18.428,25 € |
| 08/0022 | D | Kreis Lippe | 7.761,90 € |
| 08/0009 | D | Grosse Kreisstadt Kirchheim unter Teck | 6.066,60 € |
| 08/0065 | D | Stadt Bad Pyrmont | 10.682,70 € |
| 08/0020 | DE | UNIVERSITATS UND HANSESTADT GREIFSWALD | 22.534,56 € |
| 08/0044 | EE | Association of Municipalities of Estonia | 16.304,00 € |
| 08/0054 | F | Ville de Vienne | 7.525,24 € |
| 08/0049 | F | Association des Communes Jumelées du Limousin | 35.460,00 € |
| 08/0039 | F | Comité de Jumelage de Saint-Alban | 27.772,68 € |
| 08/0036 | F | Institut Europeen Seguier | 11.212,80 € |
| 08/0053 | H | Self Government of Jasz Nagykun Szolnok County | 18.279,18 € |
| 08/0103 | H | Municipality of Tata | 6.933,04 € |
| 08/0008 | H | Selbstverwaltung der Stadt Körmend | 7.431,75 € |
| 08/0045 | H | Baranya Megeyei Onkormanyzat | 11.264,70 € |
| 08/0090 | H | Somogy County Government | 13.648,20 € |
| 08/0078 | H | Kiskunmajsa Varos Onkormanyzata | 16.850,70 € |
| 08/0099 | H | Municipality of Nagyvazsony | 7.805,64 € |
| 08/0100 | HU | MORAHALOM VAROS ONKORMANYZATA | 16.998,45 € |
| 08/0076 | I | Comune di Ponte Lambro | 23.631,33 € |
| 08/0048 | I | Provincia di Bologna | 24.909,96 € |
| 08/0029 | I | Municipality of Candelo | 25.576,35 € |
| 08/0068 | I | Comune di Traversetolo | 26.356,71 € |
| 08/0031 | I | Comune di Montespertoli | 12.130,60 € |
| 08/0047 | I | Comune di Scandiano | 23.932,02 € |
| 08/0025 | I | City of Torino | 24.020,00 € |
| 08/0085 | I | Associazione Nationale Comuni del Lazio | 12.170,07 € |
| 08/0071 | I | Comune di Fontanellato | 25.867,95 € |
| 08/0058 | I | Comune di Casavatore | 23.652,36 € |
| 08/0074 | I | Comune di Codigoro | 27.231,69 € |
| 08/0069 | I | Unione Nazionale Comuni Comunita Enti Montani | 26.754,90 € |
| 08/0017 | I | Provincia di Lodi | 14.222,04 € |
| 08/0059 | I | Associazione Nationale Comuni del Lazio | 15.303,30 € |
| 08/0056 | I | Provincia Regionale di Siracusa | 28.055,20 € |
| 08/0040 | IT | COMUNE DI SPECCHIA | 26.091,93 € |
| 08/0075 | IT | PROVINCIA DI FORLI CESENA | 8.706,00 € |
| 08/0057 | IT | COMUNE DI FONTE NUOVA | 14.532,60 € |
| 08/0038 | LET | Liepaja City Culture Department | 14.359,00 € |
| 08/0062 | NL | Stichting Jumelage Bodegraven | 7.686,99 € |
| 08/0051 | P | AMPV- Portuguese Wine Municipalities | 14.290,50 € |
| 08/0101 | PL | City of Elblag | 9.184,30 € |
| 08/0043 | PL | Municipality of Bartoszyce | 6.072,84 € |
| 08/0055 | PL | Ville de Bydgoszcz | 6.628,47 € |
| 08/0098 | PL | Starostow Powiatowe w Nowy Sacz (County Office) | 18.225,40 € |
| 08/0037 | PL | Urzad Miasta I Gminy Niepolomice | 12.464,85 € |
| 08/0041 | PL | Tarnowo Podgorne Municipality | 10.776,45 € |
| 08/0032 | PL | KOMITET WSPOLPRACY GMINY WRONKI Z ZAGRANICA | 13.375,77 € |
| 08/0052 | PT | VIANA DO COSTELO | 7.020,00 € |
| 08/0012 | R | Harghita County Council | 11.047,05 € |
| 08/0077 | S | Norrbottens Läns Landsting | 17.429,70 € |
| 08/0097 | S | Vanersborg Municipality | 27.679,89 € |
| 08/0018 | S | City Of Helsingborg | 8.753,70 € |
| 08/0021 | S | City of Mölndal | 12.264,00 € |
| 08/0042 | SK | Mesto Spisska Nova Ves | 5.897,55 € |
| 08/0035 | SK | Municipality of Presov | 8.363,40 € |
| 08/0026 | UK | Preston City Council | 15.028,35 € |
| 08/0007 | UK | OXFORD CITY COUNCIL | 24.100,05 € |

| Project number | Title of the project | Applicant | Country | Maximum EU grant |
| --- | --- | --- | --- | --- |
| CP-2008-001 | Sport in 3D | Land Steiermark | Austria | 88.797,00 |
| CP-2008-003 | EU:SPORT:FUTURE | ENGSO - Liaison Office | Belgium | 149.280,40 |
| CP-2008-005 | Active Citizens for a better Europe | Association for European partnership/AEP | Bulgaria | 75.000,00 |
| CP-2008-010 | "Enhancing participation among Roma" | ERIO | Belgium | 122.562,00 |
| CP-2008-011 | Intercultural Youth Panels | Qec-ERAN | Belgium | 115.722,00 |
| CP-2008-012 | European Citizen's Panel - New democratic toolbox for new Institutions | ECAS | Belgium | 150.000,00 |
| CP-2008-021 | Europe for Youth through Intercultural Dialogue | Integrating Ireland | Ireland | 89.648,57 |
| CP-2008-025 | Winning a medal for Europe | Municipality of Skyries | Greece | 83.922,00 |
| CP-2008-026 | "L'Europe au féminin : pour une vraie parité" | Fondation Robert Schuman | France | 85.595,67 |
| CP-2008-032 | Satisfaction of Quality Information Needs of policy makers and citizens on EU and interculturality - QUIN | Fundacion AFIES | Spain | 91.657,71 |
| CP-2008-033 | All 4 EU : Citizens for Europe ! | Region of Istria | Croatia | 150.000,00 |
| CP-2008-035 | BANDIAR | Aragonese association of local authorities | Spain | 144.149,58 |
| CP-2008-036 | Do EU know ? | Fondazione caritas Ambrosiana | Italy | 99.978,00 |
| CP-2008-040 | 4: Miss you, rope! | Associazione Culturale Link | Italy | 89.911,20 |
| CP-2008-041 | Dialogue for Europe : Citizens' panel for the promotion of active citizenship | Associazione regionale comuni del Lazio | Italy | 150.000,00 |
| CP-2008-043 | Euromedinculture Citoyenneté : "Culture, création et dialogue : la culture comme outil de structuration de l'Union Européenne" | Association pour le Développement Culturel Européen et International | France | 150.000,00 |
| CP-2008-044 | ACID - Active citizens for intercultural dialogue | Università del terzo settore | Italy | 150.000,00 |
| CP-2008-045 | Stories of a Possible Europe | Unversità Popolare di Roma | Italy | 147.000,00 |

| PROJECT NR. | COUNTRY | APPLICANT | MAXIMUM GRANT AWARDED |
| --- | --- | --- | --- |
| 08/0125 | I | SWEDEN EMILIA ROMAGNA NETWORK | 45.000,00 € |
| 08/0119 | FI | SUOMEN KUNTALIITTO | 31.769,00 € |
| 08/0126 | A | STEIERMARKISCHER GEMEINDEBUND | 44.480,00 € |
| 08/0131 | LV | LATVIAN ASS.OF LOCAL AND REGIONAL GOVERNMENTS | 31.202,40 € |
| 08/0115 | BG | NATIONAL ASSOCIATION OF MUNICIPALITIES IN REP.OF BULGARIA | 44.800,00 € |
| 08/0123 | F | ASSOCIATION OF LOCAL DEMOCRACY AGENCIES | 45.000,00 € |
| 08/0121 | H | VITEA FUND | 44.960,00 € |
| 08/0117 | HR | ASSOCIATION OF MUNICIPALITIES OF THE REP. OF CROATIA | 44.000,00 € |
| 08/0127 | F | ASSOCIATION FRANCAISE DU CONSEIL DES COMMUNES ET REGIONS D' EUROPE (AFCCRE) | 45.000,00 € |
| 08/0133 | PL | ASSOCIATION OF POLISH CITIES | 35.564,00 € |
| 08/0128 | D | INSTITUT FUR SOZIALE INFRASTRUKTUR (ISIS) | 44.043,20 € |
| 08/0116 | B | VERENIGING VAN VLAAMSE STEDEN EN GEMEENTEN (VVSG) | 44.520,01 € |
| 08/0120 | D | INSTITUT FÜR EUR. PARTNERSCHAFTEN | 45.000,00 € |
| 08/0132 | I | UNIONE DEI COMUNI "DALL'ELEUTERIO A ROCCA BUSAMBRA" | 36.722,40 € |
| 08/0124 | SLO | ZAVOD ZA KULTURNE PRIREDITVE IN TURIZEM CELEIA CELJE | 44.000,00 € |
| 08/0129 | BG | UNION OF BULGARIAN BLACK SEA LOCAL AUTH. | 43.665,32 € |

| Annual grants |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref accusé réception dossier | Organisation | Pays | Eligible budget |  |
|  |  |  | Total budget | Maximal Grant |
| OG-2008-054 | Research Institute for Linguistics of the Hungarian Academy of Sciences | HU | 130.000,00 € | 55.000,00 € |
| Multiannual partnership agreements |  |  |  |  |
| Ref accusé réception dossier | Organisation | Pays | Eligible budget |  |
|  |  |  | Total budget | Maximal Grant |
| OG-2008-075 | The Lisbon Council for Economic Competitiveness and Social Renewal asbl | BE | 321.856,08 € | 150.000,00 € |
| OG-2008-077 | Friends of Europe asbl | BE | 1.527.800,00 € | 174.800,00 € |
| OG-2008-119 | Active Citizenship Foundation (FONDACA) | IT | 322.202,00 € | 60.000,00 € |
| OG-2008-055 | Trans European Policy Studies Association (TEPSA) | BE | 179.329,70 € | 110.000,00 € |
| OG-2008-028 | Centre for European Policy Studies (CEPS) | BE | 2.976.023,00 € | 120.000,00 € |
| OG-2008-005 | Confrontations Europe | FR | 966.700,00 € | 210.000,00 € |
| OG-2008-015 | European Policy Centre (EPC) | BE | 2.900.000,00 € | 150.000,00 € |
| OG-2008-020 | Istituto di Sociologia Internazionale di Gorizia (ISIG) | IT | 560.033,00 € | 53.000,00 € |
| OG-2008-068 | Centre for Economic Policy Research (CEPR) | UK | 119.942,00 € | 58.675,62 € |
|  |  |  | Total: | 1.141.475,62 € |

| Annual grants |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref accusé réception dossier | Organisation | Pays | Eligible budget |  |
|  |  |  | Total budget | Maximal Grant |
| OG-2008-076 | Mediterranean Institute of Gender Studies (MIGS) | CY | 76.630,00 € | 60.000,00 € |
| OG-2008-031 | Polska Fundacija im. Roberta Schumana | PL | 148.235,00 € | 60.000,00 € |
| OG-2008-090 | Fédération Européenne de Solidarités de Proximité (F.E.S.P) | BE | 98.000,00 € | 55.000,00 € |
| OG-2008-074 | Autonómia Alapítvány (Autonomia Foundation) | HU | 112.250,00 € | 60.000,00 € |
| OG-2008-117 | Europa Esperanto Unio (EEU) | BE | 69.930,00 € | 55.930,00 € |
| OG-2008-044 | Euradio | FR | 390.300,00 € | 60.000,00 € |
| OG-2008-132 | Association Européenne pour la défense des Droits de l'Homme (AEDH) | BE | 65.000,00 € | 50.000,00 € |
| OG-2008-071 | European Association for Viewers Interests | BE | 68.143,75 € | 54.515,00 € |
| OG-2008-012 | European Non Governmental Sports Organisation (ENGSO) | FR | 119.570,00 € | 60.000,00 € |
| Multiannual partnership agreements |  |  |  |  |
| Ref accusé réception dossier | Organisation | Pays | Eligible budget |  |
|  |  |  | Total budget | Maximal Grant |
| OG-2008-034 | European Paralympic Committee | DE | 163.289,80 € | 110.000,00 € |
| OG-2008-056 | European Citizen Action Service (ECAS) | BE | 615.947,00 € | 153.493,99 € |
| OG-2008-017 | Europäische Akademie Berlin e.V. | DE | 1.661.007,03 € | 150.000,00 € |
| OG-2008-047 | Agricultural and Rural Youth Association (AGRYA) | HU | 215.363,00 € | 80.000,00 € |
| OG-2008-050 | SOLIDAR | BE | 535.445,50 € | 142.267,87 € |
| OG-2008-032 | Union of European Federalists (UEF) | BE | 166.970,00 € | 110.000,00 € |
| OG-2008-084 | Assembly of European Regions (AER) | FR | 2.123.083,21 € | 170.683,62 € |
| OG-2008-079 | Babel International | FR | 315.124,60 € | 100.000,00 € |
| OG-2008-007 | Netzwerk Migration in Europa e.V. | DE | 202.306,00 € | 84.430,00 € |
| OG-2008-070 | Centre Européen Juif d'Information (CEJI) | BE | 482.519,28 € | 50.000,00 € |
| OG-2008-135 | Verein für Sprach – und Kulturaustausch in Mittel – Ost und Südeuropa (Mit Ost e.V.) | DE | 285.476,75 € | 110.000,00 € |
| OG-2008-009 | Internationales Kolpingwerk (IKW) | DE | 105.000,00 € | 80.000,00 € |
| OG-2008-036 | The Association of Service Civil International in Europe ivzw | BE | 222.206,00 € | 110.000,00 € |
| OG-2008-043 | Centre européen de volontariat (CEV) | BE | 153.494,71 € | 108.633,80 € |
| OG-2008-052 | Future of Europe Association (EJE) | HU | 101.442,00 € | 50.000,00 € |
| OG-2008-129 | Heinrich-Böll-Stiftung (hbs) | DE | 397.743,00 € | 150.000,00 € |
| OG-2008-120 | Association of the Local Democracy Agencies (ALDA) | FR | 756.430,00 € | 210.000,00 € |
| OG-2008-099 | The Intercultural Communication and Leadership School / Scuola di Comunicazione e Leadership Interculturale (ICSL) | IT | 203.900,00 € | 110.000,00 € |
| OG-2008-148 | Fundacion Academia Europea de Yuste (FAEY) | SP | 720.419,94 € | 176.502,89 € |
|  |  |  | Total: | 2.771.457,17 € |

| Ref accusé réception dossier | Project title | Bénéficiaire | Ville | Pays | Budget based (BB) or Lump Sum (LS) | Maximum grant |
| --- | --- | --- | --- | --- | --- | --- |
| CSP-2008-006 | Zugang zum Arbeitsmarkt durch assistierende Technologien. Neus allheilmittel? | Evangelisches Hilfswerk in Osterreich (Diakonie Auslandhilfe) | Wien | AT | LS | 29.874,80 € |
| CSP-2008-020 | EU 55 + | SPES Bildungs und Studien GmbH | Schlierbach | AT | BB | 55.000,00 € |
| CSP-2008-026 | EU-Strategie Gender Budgeting | Netzwerk österreichischer Frauen und Mädchenberatungsstellen | Wien | AT | LS | 31.837,70 € |
| CSP-2008-073 | Europa Multiplikatorlnnen 08/09 | Bund Europäiscger Jugend / Junge Europäische Föderalisten Österreich – (BEJ/JEF)-Ö (Europajugend) | Wien | AT | LS | 37.088,48 € |
| CSP-2008-081 | Klassentreffen | Institut fuer Wissenschaftskommunikation und Hochschulforschung | Wien | AT | BB | 55.000,00 € |
| CSP-2008-101 | CivilMedia 08-UnConference Intecultural Dialogue 2.0 | Radiofabrik | Salzburg | AT | LS | 40.092,00 € |
| CSP-2008-167 | 72 Stunden ohne Kompromiss | Katholische Jugend Österreich (KJÖ) | WIen | AT | BB | 55.000,00 € |
| CSP-2008-223 | Black European Women's Network (BEWNET) | AFRA-International Center for Black Women's Perspectives | Vienna | AT | LS | 55.471,72 € |
| CSP-2008-242 | Kompass zivilgesellschaftliches Engagement | Förderverein der Volkshochschule Wien-Nordwest, Alsergrund, Währing, Döbling (VHS Alsergrund) | Wien | AT | LS | 21.500,60 € |
| CSP-2008-249 | Beiträge von Migrantlnnen und Flüchtlingen zur Demoktatieentwicklung in Europa- Möglichkeiten zivilgesellschaftlicher Partizipation | Verein von Ausländerlnnen-betreuerlnnen asylkoordination österreich | Wien | AT | LS | 14.659,50 € |
| CSP-2008-279 | YouthNET - A network for European SEEtizens | Interkulturelles Zentrum | Vienna | AT | LS | 47.198,50 € |
| CSP-2008-013 | LINKS | European Association of Service Providers for Persons with Disabilities (EASPD) | Brussels | BE | LS | 30.712,82 € |
| CSP-2008-015 | Heritage Care through Active Citizenship and vice versa | Heemkunde Vlaanderen vzw | Mechelen | BE | LS | 47.535,00 € |
| CSP-2008-025 | Réseau européen des Radios d'étudiants en journalisme | Institut des hautes etudes des communications sociales « Haute Ecole Galilée » | Bruxelles | BE | LS | 22.667,55 € |
| CSP-2008-029 | VERS UN ERASMUS SYNDICAL: mise en réseau des travailleurs des organisations syndicales de l'UE | Confédération européenne des syndicats (CES) | Bruxelles | BE | BB | 55.000,00 € |
| CSP-2008-037 | Micronomics | VZW City Mine(d) | Bruxelles | BE | LS | 39.547,20 € |
| CSP-2008-068 | Being a Citizen of Europe and a Person of Faith. Christians and Muslims as Active Partners in European Societies. European Christian-Muslim Conference | Church & Society commission of the Conference of European Churches (CSC) | Bruxelles | BE | LS | 26.172,32 € |
| CSP-2008-086 | Cascade Europe | ECAS - European Citizen Action Service | Bruxelles | BE | LS | 41.026,50 € |
| CSP-2008-096 | Intercultural Dialogue Day | European Federation for Intercultural Learning (EFIL) | Bruxelles | BE | LS | 25.526,20 € |
| CSP-2008-120 | European Conference on Civic Service-an exchange of practices and strategies | AVSO-Association of Voluntary Service Organisations | Bruxelles | BE | LS | 36.872,00 € |
| CSP-2008-130 | The future of Intellectual Property - Ensuring Creativity and Innovation in the Digital Era | Goethe-Institut e.V. (Brussels Branch Office) | Bruxelles | BE | LS | 23.479,60 € |
| CSP-2008-134 | The Consumer Pact for the 2009 European Elections | Bureau Européen des Unions des Consommateurs (BEUC) | Bruxelles | BE | BB | 55.000,00 € |
| CSP-2008-153 | Projet CID - Citoyenneté, interculturalité, Dialogue | Pôle européen des fondations de l'économie sociale | Bruxelles | BE | BB | 54.406,29 € |
| CSP-2008-203 | EU Values : The Roma Migration Challenge | International Society for Sustainable Development and Cooperation (ISSDC) | Sofia | BG | LS | 24.994,26 € |
| CSP-2008-271 | Women in political life for a successful Europe | Assiciation for European Partnership (AEP) | Sofia | BG | LS | 12.619,20 € |
| CSP-2008-273 | Heritage Management and Urban Development | Association for sustainable development and analyses | Plovdiv | BG | LS | 24.966,90 € |
| CSP-2008-234 | Reform Treaty: What's the Need 4U | European Institute of Cyprus (EIC) | Nicosia | CY | BB | 54.831,00 € |
| CSP-2008-047 | Next Europe - Reformatory, Cross cultural, Equal, Integrated? | Občanský institut (Civic Institute) | Prague | CZ | LS | 36.597,57 € |
| CSP-2008-162 | European Values Network 2009 (EVN 09) | Evropske hodnoty o.s. | Praha 4 | CZ | LS | 37.008,45 € |
| CSP-2008-175 | The European City : - ensuring social cohesion in a rapidly changing world | Multicultural Center Prague | Prague | CZ | LS | 45.222,40 € |
| CSP-2008-001 | Geeint in Vielfat-8 Nationen in Dialog | Internationales Begegnungszentrum St. Marienthal | Ostritz | DE | LS | 52.656,00 € |
| CSP-2008-005 | Aktive Bürger gestalten Europa | Forum Europa e.V. | Leipzig | DE | LS | 23.973,60 € |
| CSP-2008-022 | RADAR ( Rural-Areas-Defence-Against Racism) | EZBB des Regionalen Fordervereins e.V | Pinnow | DE | LS | 40.206,30 € |
| CSP-2008-056 | Egeria Weg - Ökumenischer Frauenpilgerweg für ein gemeinsames Europa | Ökumenisches Forum Christlicher Frauen in Europa Bereich Deutschland e.V. | Braunschweig | DE | LS | 22.462,30 € |
| CSP-2008-108 | European Global Education Days 2008 | Internationale Weiterbildung und Entwicklung gGmbH- InWEnt | Berlin | DE | LS | 38.686,50 € |
| CSP-2008-115 | Das Grundeinkommen auf dem Weg nach Europa | Bildungswerk Berlin der Heinrich Boll Stiftung | Berlin | DE | LS | 47.376,00 € |
| CSP-2008-122 | Model International Criminal Court (MICC) | Kreisau-Initiative Berlin e.V. | Berlin | DE | LS | 24.897,78 € |
| CSP-2008-123 | Gesundheit-hochstes Gut? | Diozesan -Caritasverband fur das Erzbistum Koln e.V | Koln | DE | LS | 21.435,90 € |
| CSP-2008-124 | EU-Kompetenz fur Migranten und Benchteiligte | Berlin-Brandenburgische Auslandsgesellschaft e.V. (BBAG) | Potsdam | DE | LS | 40.471,58 € |
| CSP-2008-126 | Europa für die Jegend - Deutsch-polnische Lehrekonferenz in Berlin | Zeitbild Stiftung | München | DE | LS | 37.091,61 € |
| CSP-2008-128 | Europa mitgestalten und Demokratie (er-) leben: Die Bürger und der Lissabon-Vertrag | Internationales Kolpingwerk (IKW) | Köln | DE | LS | 26.966,45 € |
| CSP-2008-129 | Weimarer Sommerkurse 2008: "Das europäische Kulturerbe - Ergebnis Ausgagspunkt interkultureller Dialoge" | Weimar-Jena-Akademie Verein für Bildung e.V. (WJA) | Weimar | DE | LS | 48.692,88 € |
| CSP-2008-145 | EURvote- EURvoice | Katolische Arbeitnehmerbewegung Deutschlands e.V. (KAB Deutschlands) | Köln | DE | BB | 55.000,00 € |
| CSP-2008-192 | Let's Debates: Citizens Media for Europe | Bürgermedienzntrum Bennohaus | Münster | DE | LS | 39.857,67 € |
| CSP-2008-202 | Challenges to Europe (OpenFora 2008/2009) | Citizens of Europe | Berlin | DE | LS | 35.515,38 € |
| CSP-2008-209 | International Session of the European Youth Parliament in Leuven | Heinz-Schwarzkopf-Stiftung/European Youth Parliament (HSS/EYP) | Berlin | DE | LS | 51.263,52 € |
| CSP-2008-224 | European Citizens' Seminar 2008-2009 | European Citizens' Seminar e.V. | Erfurt | DE | LS | 23.614,20 € |
| CSP-2008-286 | Creating Forum Pécs | Stiftung Zukunft Berlin | Berlin | DE | LS | 24.763,81 € |
| CSP-2008-012 | BS-NGO FORUM 2009 | Danish Core Group Baltic Sea NGO Forum (DANFO) | Copenhagen | DK | LS | 57.988,00 € |
| CSP-2008-080 | Rural Voice | European Rural Alliance (ERA) | Arrakoski | FI | BB | 30.126,00 € |
| CSP-2008-111 | Going local-Civic participation at local level and in a European context | Educational Association Citizens'Forum (Sivistysliitto Kansalaisfoorumi SKAF ry) | Vantaa | FI | LS | 11.906,15 € |
| CSP-2008-155 | Baltic Europe Consultation (BEC) | Eurooppalainen Suomi ry | Helsinki | FI | LS | 31.277,44 € |
| CSP-2008-007 | L'Europe des Citoyens pour Tous: les personnes handicapées en mouvement | European Blind Union (EBU)- Union Européenne des Aveugles (UEA) | Paris | FR | LS | 41.370,15 € |
| CSP-2008-050 | Intervisions urbaines- 4 jours et 4 nuits pour un court | Plan Large | Guernes | FR | LS | 37.066,69 € |
| CSP-2008-058 | 2009,Tous aux urnes | Idées Nouvelles Europe | Le Mas | FR | BB | 53.034,00 € |
| CSP-2008-079 | 14ème Université de la Formation, de l'Education et de l'Orientation (14éme UFEO) - "L'Europe de la Formation : Ambitions communautaires et réalisations concrètes" | Maison de la Promotion Sociale (MPS Aquitaine) | Artigues-près-Bordeaux | FR | LS | 27.680,25 € |
| CSP-2008-091 | Colloque européen: le sport à l'épreuve de la diversité culturelle | Agence pour l'Education par le sport (APPELS) | Paris | FR | LS | 31.920,70 € |
| CSP-2008-106 | Europe 'plus': proximité, communauté, solidarité | Réalités Européennes du Présent c/o Maison de l'Europe de Paris | Paris | FR | LS | 24.869,22 € |
| CSP-2008-121 | Contribuer à une Europe solidaire avec des personnes ayant un handicap mental | Fédération Internationale des Communautés de l'Arche | Compiègne | FR | LS | 15.224,05 € |
| CSP-2008-138 | EU Campaign on the Ground | Babel international | Paris | FR | LS | 29.928,24 € |
| CSP-2008-151 | 2èmes Assises Européennes du Plurilinguisme | Assoc. Européenne pour la diffusion sur la recherche, l'Europe et la société | Paris | FR | LS | 37.806,05 € |
| CSP-2008-182 | Citoyens de l'Europe des Lettres: des cultures en dialogue | Les Lettres Européennes (LLE) | Wemaers-Cappel | FR | LS | 27.894,96 € |
| CSP-2008-204 | Semaine de rencontres islamo-chrétiennes 2008 | Groupe d'amitié islamo-chrétienne (GAIC) | Paris | FR | LS | 22.684,00 € |
| CSP-2008-212 | Citoyenneté Européenne et Esprit d'Entreprendre: 3èmes rencontres de jeunes européens issus des viles du réseau CINTE | Cités Intermédiaires Européennes (CINTE) | Massy | FR | LS | 50.053,30 € |
| CSP-2008-213 | Taste: Food and Culture | NISI MASA (European Network of Young Cinema) | Paris | FR | LS | 40.080,82 € |
| CSP-2008-216 | Le Franco-Allemand: un pivot pour l'Europe | Association Point Jeunes | Evreux | FR | LS | 49.643,46 € |
| CSP-2008-238 | Pour des eco-citoyennes actives en Europe | Centre méditerranéen de l'environnement (CME) | L'Isle sur la Sorgue | FR | BB | 53.062,00 € |
| CSP-2008-250 | Training for Active Citizenship in the EU Enlargement Process | Association of Local Democracy Agencies (ALDA) | Strasbourg | FR | LS | 17.232,51 € |
| CSP-2008-287 | Reforming EU | Hellenic Committe for European Union | Athens | GR | LS | 29.437,02 € |
| CSP-2008-072 | Role of Youth in Peace-Building Process | Center for Peace Studies / Centar za mirovne studije (CPS/CMS) | Zagreb | HR | LS | 10.052,32 € |
| CSP-2008-104 | Istria Communicating Europe | Foundation for Partnership and civil society development | Pula | HR | BB | 46.395,58 € |
| CSP-2008-228 | FERRY BOAT- Split-Ancona inter-cultural dialogue through volunteering | Association "MI" | Split | HR | LS | 13.388,40 € |
| CSP-2008-008 | Development of an Efficient Representation of Agricultural Interests after the Reform Treaty | Agricultural and Rural Youth Association (AGRYA) | Budapest | HU | LS | 17.074,20 € |
| CSP-2008-043 | Bécs-Pozsony-Budapest Szupermaraton Sport- és Turisztikai Fesztivál | Pest Megyei Atlétikai Szövetség (PASZ) | Budapest | HU | LS | 54.953,76 € |
| CSP-2008-054 | Civiliada 2008 - Partnership for Europe | European House | Budapest | HU | LS | 16.698,70 € |
| CSP-2008-075 | For the Protection of Citizens | Association of Civil Guards and Firemen of Pilisszentiván (Civil Guards od Pilisszentiván) | Pilisszentiván | HU | LS | 24.945,12 € |
| CSP-2008-077 | Providing Free Acces to the Elderly in Culture | Hungarian Association of Pensioners' Club And of Elderly People (Nyugdíjasklubok Országos Szövetsége) | Budapest | HU | LS | 13.825,20 € |
| CSP-2008-087 | Central European Trail-O League | MTFSZ - Magayar Tajekozodasi Futo Szovetseg | Budapest | HU | LS | 20.650,35 € |
| CSP-2008-094 | Election Stakeholders for reintegrating European citizens | ACEEEO (Assocciation of European Election Officials) | Budapest | HU | LS | 17.823,30 € |
| CSP-2008-103 | International Workshop including a theatre performance and a sysmposium, with the participation of homeless people and experts dealing with drama therapy, with a view to creating a professional network and generating future international projects | Budapest Organisational Unit of Hungarian Red Cross | Budapest | HU | LS | 24.293,10 € |
| CSP-2008-107 | Civilians in the Carpathian basin | Civil Radiozasert Alapitvany (Foundation for Civil Radio Broadcasting) | Budapest | HU | LS | 23.833,16 € |
| CSP-2008-127 | Green Bikes for Peace | (Hungarian Cyclists' Club) Magyar Kerékparosklub | Budapest | HU | LS | 35.371,39 € |
| CSP-2008-131 | Discussions about Equality | Kristály Alapítvány | Nyíregyháza | HU | LS | 24.026,40 € |
| CSP-2008-140 | Zwei Kulturen- ein Dialog | Minderheitenselbstverwaltung der Ungrarndeutschen in Budapest XVIII. Bezirk ( Budapest XVIII. Keületi Német Kisebbségy Önkormányzat) MSV/NKÖ | Budapest | HU | LS | 14.528,11 € |
| CSP-2008-148 | EUROPLIKATOR: European Multiplicator Training for Teachers and NGOs | Anthropolis Anthropological Public Benefit | Budapest | HU | LS | 16.386,46 € |
| CSP-2008-152 | JCI- Trainings for improving active European citizenship | JCI - Europai Konferencia 2009 Kozhasznu Alapitvany | Veresegyhaz | HU | LS | 16.561,65 € |
| CSP-2008-156 | System for exploiting the European, national and local intellectual fund | Innoratio Kutatomuhely | Szeged | HU | LS | 9.079,74 € |
| CSP-2008-160 | Hier und Jetzt | Nagyito Alapitvany | Szeged | HU | LS | 27.178,50 € |
| CSP-2008-161 | Csango Festival | Folklor Kulturalis Kozalapitvany | Jaszbereny | HU | LS | 22.306,80 € |
| CSP-2008-164 | Renewable energies against poverty (REP) | Interregionalis Megujulo Energia Klaszter Egyesulet | Pecs | HU | LS | 21.136,00 € |
| CSP-2008-166 | Generations cooperation / Kooperation der Generationen / GECO | Budakeszi Europa Társaság (BET) | Budakeszi | HU | LS | 24.568,52 € |
| CSP-2008-170 | Let's talk about Europe' symposium and conferences | HÖOK a Hallgatókért Alapítvány (National fund for Students in Hungary) ( HÖOK) | Budapest | HU | LS | 14.460,50 € |
| CSP-2008-191 | Promotion of good practices for equal access and opportunities for people with autism (ASD) in Hungary and in Central Europe, through intensifying Hungarian and broadening inter-European professional association-system | Autism Professional Society | Budapest | HU | LS | 15.506,55 € |
| CSP-2008-196 | Chit pa de (I love you in Burman language) - multicultural contents and intercultural education by using of experimental education | Zabhegyezo Gyerekanimatorok Egyuesülete | Budapest | HU | LS | 22.318,50 € |
| CSP-2008-210 | Cultural Rights of the Sign Language Community in Europe | Hungarian Association of the Deaf and Hard of Hearing (SINOSZ) | Budapest | HU | LS | 24.674,00 € |
| CSP-2008-229 | Citizens' learning exchange in developing their communinities | Carpathian Foundation International (CFI) | Eger | HU | LS | 21.087,75 € |
| CSP-2008-272 | Sport for friendship and European Citizenship | Magyar Labtoll-labda Szovetseg | Ujszasz | HU | LS | 24.530,75 € |
| CSP-2008-082 | Making Europeans Through Rights: European Festival of Diversities and anti-discrimination | Movimento d'Identita Transsesuale | Bologna | IT | LS | 39.592,54 € |
| CSP-2008-144 | Descrescere e stili di vita, sostenibilità ambientale, partecipazione e convivialità…in Europa! | INSIEME società cooperativa sociale a r.l. | Vicenza | IT | LS | 24.152,40 € |
| CSP-2008-180 | Creative means and network for European intercultural tourism | Circolo U.S. A.C.L.I. Associazione Sportiva Dilettantistica Compagnia del Buon Cammino (ASDCBC) | Cuneo | IT | LS | 21.603,90 € |
| CSP-2008-189 | Noi Europei | Accademia Europeista del F.V.G. | Gorizia | IT | LS | 15.168,55 € |
| CSP-2008-219 | SAVE-Sport Against Violence in Europe | Comitato Territoriale UISP Cirié Settimo Chivasso | Cirie | IT | LS | 41.074,66 € |
| CSP-2008-222 | Espoir I-Engagement sur possibilités d'Initiatives de Rencontre Interculturel | Confederazione Geerale Italiana del Lavoro (C.G.I.L) Lombardia | Sesto S.Giovanni | IT | BB | 49.970,00 € |
| CSP-2008-230 | Dialogue Watch | Fondazione Mezzogiorno Europa | Napoli | IT | LS | 38.984,36 € |
| CSP-2008-251 | CIPEAC - Creativity and Innovation in the Promotion of European Active Citizenship | Centro Europa Scuola Educazione E Società (C.E.S.E.S) | Milano | IT | LS | 48.404,08 € |
| CSP-2008-257 | Let's raise the Curtain ! Creative workshop to improve the participation of rural women to local development | Centro Studi ed Iniziative Europeo | Trappeto PA | IT | LS | 42.787,02 € |
| CSP-2008-265 | Two teams One heart | CINETICA | Rome | IT | BB | 24.600,00 € |
| CSP-2008-267 | Shots of Dialogue | Associazione Culturale Link (LINK) | Altamura | IT | LS | 24.889,78 € |
| CSP-2008-269 | Right to Information - right to citizenship | Argonauti | Palermo | IT | LS | 43.944,28 € |
| CSP-2008-071 | Getting Above "Being The Second Place" - Networking Skills for Musical and Cultural Multipliers in East and West Europe | MountainRock | Kaunas | LT | LS | 20.203,20 € |
| CSP-2008-169 | Know how for active society involvement in youth prevention : intercultural context | Klaipeda District Education Centre (Klaipeda District EC) | Gargzdai | LT | LS | 9.144,48 € |
| CSP-2008-173 | Art - Common language of European citizens' | Administration of Trakai Region Municipality | Trakai | LT | LS | 22.771,50 € |
| CSP-2008-195 | Senior in a focus | The Volunteer Centre (Savanoriu centras) | Vilnius | LT | LS | 14.240,58 € |
| CSP-2008-198 | Being citizens in Europe | Informal training centre for adults and young people of Radviliskis district municipality | Radviliskis | LT | LS | 10.699,92 € |
| CSP-2008-275 | Citizenship Initiatives - Main instrument towards democratic society | Western Lithuania Consumer Federation | Klaipeda | LT | LS | 14.742,30 € |
| CSP-2008-143 | EU-ALLINC (Europe All Included) | Tiye International | Utrecht | NL | BB | 24.980,00 € |
| CSP-2008-277 | Celebration of Dialogue and Debate Exchange - training and networking | IDEA - International Debate Education Association | Amsterdam | NL | LS | 30.367,20 € |
| CSP-2008-034 | European Parliament for Youth (EPY) | Center for Citizenship Education | Warsaw | PL | LS | 20.710,00 € |
| CSP-2008-055 | Immigrants Inc. - The 4th International Meeting of European Schools | Polska Fundacja im. Roberta Schumana/The Polish Robert Schuman Foundation | Warsaw | PL | LS | 18.631,76 € |
| CSP-2008-105 | Social Integration trhough sport | Miejski Klub Sportowy w Gogolinie | Gogolin | PL | LS | 22.367,52 € |
| CSP-2008-141 | Ist das private Politisch? Selbstbestimmung von Europäerinnen | Goethe-Institut e.V. Krakau | Krakau | PL | LS | 12.812,40 € |
| CSP-2008-280 | Debata spoleczna: Europejczycy: rozni i rowni | Wyzsza Szkola Bankowa w Poznaniu | Poznan | PL | LS | 12.121,83 € |
| CSP-2008-172 | Step into Europe | Associação Juvenil da Linha de Cascais Rota Jovem (Rota Jovem) | Cascais | PT | LS | 24.925,20 € |
| CSP-2008-109 | Learning about us-Europe closer to citizens in rural environment | Societatea Romana Pentru Educatie Permanenta (Romanian Society for Lifelong Learning) | Bucharest | RO | BB | 55.000,00 € |
| CSP-2008-193 | Promoting Active European Citizenship through Cultural Heritage | Transylvania Trust | Cluj Napoca | RO | LS | 19.664,00 € |
| CSP-2008-088 | MenEngage Europe Networking Seminar/Workshop | Män för Jämställdhet (Men for gender Equality) MfJ | Stockholm | SE | LS | 24.987,15 € |
| CSP-2008-114 | Active an Transnational Citizenship Program (Actransit) | European Alternatives Limited | Houghton, Huntingdom | UK | LS | 24.846,77 € |
| CSP-2008-139 | European Youg defenders' Network (EYDN) | Fair Trials International | London | UK | LS | 31.018,20 € |
| CSP-2008-146 | Europe 2.0 - Don't ask what Europe can do for you but what you can do for Europe | Euclid Network | London | UK | BB | 54.995,04 € |
| CSP-2008-190 | Take part in Europe | Community Service Volunteer | London | UK | LS | 40.792,40 € |
| CSP-2008-274 | Europe Matters | CFOR - Force for Change | London | UK | LS | 24.947,00 € |
| Somme totale des subventions proposées à la sélection |  |  |  |  |  | 4.079.919,88 € |

- Annex 12 Action 3 – Together for Europe “Golden Stars” attribution 2008

- Civil Society projects

- The Organized Civil Society: New Tasks in an Enlarged European Union, an Italian project of the Euromed Carrefour Sicilia, with partners from RO, UK,  PT, AT, CZ and PL

- EUReporter, a French project of the Babel International Association, with partners from CZ, BE, PL, HU, EE, PT, LT, DE, RO

- Bring Europe Closer to Youth – Simulation of the Summit of the European Council, a project of the Polish Robert Schuman Foundation with partners from PL, ES, IT, CZ,  LV, DE, FR, SK and HU

- Remembrance Projects

- The Trans-national Culture of Remembrance at the Dachau Concentration Camp Memorial Site: Preserving the International Victims Testimonies for Future Generations, a German project of the International Committee of Dachau with partners from FR, CZ, NL, AT, BE, LU, HU, SI, RO, BG

- Daughters of the Enemy, a Czech project of the NGO Docs, Youth and Society with partners from IT and DE

- The Neighbours Who Disappeared – Tribute of the Child Holocaust Victims, a Czech project of the organisation: ‘The forgotten ones’, with partners from IT, DE and UK.

- Town Twinning Projects

- Reichelsheim (DE) for the meeting: The Future of the European Union – Consequences and Perspectives of Enlargement in view of German – French, German-Polish and German-Hungarian Town Twinning Partnerships. Participating countries: FR, PL and HU.

- Bojnice (SK) for their Meeting of the Citizens of Partner Towns. Participating countries: DE, CZ, IT and PL.

- Bialogard (PL) for the meeting: Magic 27 – the Future of Common Europe. Participating countries: BE, SE, LV and RO.

- Association of twinning committees of Puy de Dôme (FR) for the European Youth Meeting: "Mobility of Young People in Europe". Participating countries: DE, UK, NL, RO, IT, PT and PL.

- Municipality of Amaroussion (EL) for the thematic networking project: Forum of the EU Citizens and Municipal Officers: Fighting for Q-cities, Fighting for a Better Daily Life. Participating countries: IT, CY, PT, NL, BE, RO and SE.

- Plérin (FR) for the thematic networking project: Sustainable Development – Issue for European Citizens. Participating countries: IE, PL and RO.

## Annex 13   			List of Europe for Citizens Points

Austria
Europe for Citizens Point Austria
Federal Ministry for Education, Arts and Culture

Belgium (NL)
Europe for Citizens Point
Cultuur Contactpunt Vlaanderen (Cultuur, Jeugd, Sport en Media)

Belgium (FR + DE)
Europe for Citizens Point
CCP Cultural contact point fort he French and the German communities

Bulgaria
Europe for Citizens Point
Directorate for information, public relations and euro-communication, 
Ministry of Foreign Affairs

Croatia

Europe for Citizens Point Croatia

Government of the Republic of Croatia - Office for Cooperation with NGOs

Czech Republic
Europe for Citizens Point Czech Republic
Eurocentrum Prague - Kontaktní místo programu Evropa pro občany

Denmark

Europe for Citizens Point

Local Government Denmark

Finland
Europe for Citizens Point Finland
CIMO (Centre for International Mobility)

France
Europe for Citizens Point France
CIDEM (Association civisme et démocratie)

Germany
Europe for Citizens Point Germany
Kontaktstelle Deutschland Europa für Bürgerinnen und Bürger
bei der Kulturpolitischen Gesellschaft e.V

Greece
Europe for Citizens Point
Ministry of Interior

Hungary
Europe for Citizens Point Hungary
TPF Tempus Public Foundation (Tempus Kozalapitvany)

Ireland
Europe for Citizens Point Ireland
IPA (Institute of Public Administration)

Italy
Europe for Citizens Point Italy
Antenna Europea Cittadini

Latvia
Europe for Citizens Point Latvia
Ministry of Culture of the republic of Latvia

Lithuania
Europe for Citizens Point Lithuania
Tarptautinių kultūros programų centras (International Cultural Programme Centre)

Malta
Europe for Citizens Point
EU affairs and policy development directorate
Ministry for tourism and culture

Netherlands
Europe for Citizens Point Netherlands
Contactpunct Europa voor de Burger
Ministry of the Interior and Kingdom relations

Poland
Europe for Citizens Point Poland
Adam Mickiewicz Institute
Punkt Kontaktowy Europa dla Obywateli
Ul. Mokotowska 25

Romania
Europe for Citizens Point Romania
CCECP Consultancy Centre for European Cultural Programmes

Slovenia
Europe for Citizens Point

Ministrstvo za kulturo RS / Ministry of Culture RS

Sweden
Europe for citizens point Sweden
Swedish association of local authorities and regions

Spain
Europe for Citizens Point Spain
PEC (Punto Europeo de Ciudadanía)

UK
Europe for Citizens Point UK
Euclid (UK) Limited

| Ref accusé réception dossier | Titre du projet | Bénéficiaire | Pays | Maximum EU grant |
| --- | --- | --- | --- | --- |
| REM-2008-032 | Museum Kreuzstadl. Der Südostwallbau | Rechnitzer Flüchtlings und Gedenkinitiative (RE.F.U.G.I.U.S.) | AT | 55.000,00 |
| REM-2008-070 | Archäologische Sicherung und öffentliche Kontextualisierung letzter baulicher Überreste des KZ Ebensee | Zeitgeschichte Museum und KZ-Gedenkstätte Ebensee (ZME) | AT | 30.000,00 |
| REM-2008-081 | Das Dreieck meiner Kindheit | Verein Freies Radio Wien | AT | 55.000,00 |
| REM-2008-087 | Internationale Gedenk und Befreiungsfeier Mauthausen 2009. Widerstand gegen den Nationalsozialismus aus religiöser Motivation | Mauthausen Komittee Österreich | AT | 14.311,00 |
| REM-2008-108 | Kinder der Taeter. Kinder der Opfer | Wiener-Krakauer Kulture - Gesellschaft (WKKG) | AT | 30.000,00 |
| REM-2008-113 | Die Kunst der Errinerung | Okto Community GmbH | AT | 55.000,00 |
| REM-2008-119 | Vergessene Opfer | Verein Schloss Hartheim | AT | 12.000,00 |
| REM-2008-127 | Niemals Vergessen - ein Hörmahnmal | Radiofabrik | AT | 55.000,00 |
| REM-2008-018 | Séminaire fondateur du Réseau Européen des Passeurs de mémoire | Fondation d'utilité publique "Maison Européenne pour le Rayonnement de la Citoyenneté" / Fondation M.E.R.Ci | BE | 19.857,90 |
| REM-2008-035 | Writing the history of the Second World War in Europe | CEGES (Centre d'Etudes et de Documentation Guerre et Scietes) | BE | 14.501,26 |
| REM-2008-084 | Le convoi | Mediel | BE | 55.000,00 |
| REM-2008-100 | Lessons from the past and the values of the United Europe | National Endowment Fund "13 Centuries of Bulgaria" | BG | 13.710,00 |
| REM-2008-009 | Czechoslovak Political Prisoners: Oral Histories of Victims of Stalinism | ANO pro Evropu o.s. (YES for Europe) | CZ | 31.374,80 |
| REM-2008-013 | Threat of Neo-Nazism and Signs of Xenophobia at present day | Památnik Lidice, grant organisation of the Ministry of Culture of the Czech Republic | CZ | 22.149,20 |
| REM-2008-075 | The database of Testimonies from Holocaust Survivors and Witnesses | Jewish Museum in Prague | CZ | 29.250,00 |
| REM-2008-088 | Stories of injustice | Clovek v tisni, ops | CZ | 55.000,00 |
| REM-2008-002 | Donauschwaben und Serben - Zusammenleben in der multiethnischen Region Vojvodina (SRB) | Stiftung Donauschwäbisches Zentralmuseum (DZM) | DE | 55.000,00 |
| REM-2008-015 | Europäische Perspektiven der Gedenkstättenpädagogik zur NS-Zeit in Frankreich, Belgien und Deutschland | Landeszentrale für politische Bildung Rheinland-Pfalz / NS-Dokumentationszentrum Rheinland-Pfalz in der Gedenkstätte KZ Osthofen | DE | 16.108,50 |
| REM-2008-019 | Erinnern für die Zukunft Europas | Internationales Begegnungszentrum St. Marienthal | DE | 42.016,50 |
| REM-2008-021 | "Ich bin als Mensch geboren und will als Mensch hier raus!" Der Geschlossene Jugendwerkhof Torgau im Erziehungssystem der DDR | Initiativgruppe Geschlossener Jugendwerkhof Torgau e.V. | DE | 55.000,00 |
| REM-2008-022 | "Erinnern und Meschenrechte. Mit der Geschichte lernen für die Zukunft Europas" | Aktion Süchnezeichen Friedensdienste e.V. | DE | 37.942,94 |
| REM-2008-076 | Aus der Vergangenheit lernen!? Lebensgeschichte als Argument | Staette der Begegnung e.V. Institut fuer Bildung und Kommunikation | DE | 28.071,34 |
| REM-2008-083 | European dimensions of forced Labour under National Socialism: mobile Exhibition on the case study of Southern Lower Saxony/Germany | Fachhochschule Hannover: Facultät III- Medien, information and design | DE | 55.000,00 |
| REM-2008-089 | Das zentrale Untersuchungsgefangnis des Kommunistischen Staatssicherheitsdienstes in Deutschaland im Spiegel von Opferberichten | Gedenkstatte Berlin-Hohenschönhausen | DE | 40.098,00 |
| REM-2008-103 | Gedächtnis für Vergangenheit - Schicksal der Zwangsarbeiter des, Dritten Reiches' als Botschaft für die Generationen Europas | Schwarzwald-Gymnasium Triberg | DE | 19.484,58 |
| REM-2008-001 | Configuaration, Purchase of Equipment for the Room of Audiovisual Information and Creation of Audioviusual Presentation for the Museum of Nazi Victims | Municipality of Distomo | EL | 54.600,00 |
| REM-2008-031 | Informing and Raising Awareness on the Holocaust by Bullets in Europe | Tyahad - In Unum | FR | 55.000,00 |
| REM-2008-059 | Journées d'étude et de formation pour les enseignants Université d'été en Pologne | Mémorial de la Shoah | FR | 22.271,00 |
| REM-2008-060 | Journées d'étude et de formation pour les enseignants Université d'été à Paris | Mémorial de la Shoah | FR | 30.611,00 |
| REM-2008-061 | Journées d'étude et de formation pour les enseignants | Mémorial de la Shoah | FR | 49.892,00 |
| REM-2008-062 | Cycle de colloques et séminaires du Mémorial de la Shoah | Mémorial de la Shoah | FR | 43.894,55 |
| REM-2008-082 | Les voix étouffées du III Reich | Forum Voix Etouffées | FR | 44.474,82 |
| REM-2008-124 | Exploring the memories of Women Victims of Nazism and Undemocratic Regimes in Research and Teaching | Centre for Women's Studies | HR | 12.925,23 |
| REM-2008-114 | Holocaust Education Project | Partners Hungary Foundation | HU | 12.556,00 |
| REM-2008-120 | Utak a gyokerekhez | Pecs-Baranya Ethnic Circle of Germans in Hungary | HU | 24.153,67 |
| REM-2008-010 | La deportazione e l'internamento dei siciliani nei campi nazisti durante la Seconda Guerra Mondiale. Elaborazione, archiviazione, documentazione e analisi delle testimonianze orali | Associazione nazionale reduci dalla prigionia, dall'internamento e dalla guerra di liberazione (A.N.R.P.) | IT | 55.000,00 |
| REM-2008-094 | The forgotten among the forgotten : remembering the past to built future cohesion | Servizio Civile Internazionale (SCI) | IT | 34.609,86 |
| REM-2008-106 | I Giusti e la resistenza al totalitarismo | Liceo Scientifico Statale "EnricoFermi" | IT | 54.600,00 |
| REM-2008-110 | Apriamo il cassetto della storia: Viaggio nella memoria | Associone "Icare formazione e sviluppo Onlus" | IT | 31.386,66 |
| REM-2008-116 | The memory of the future: from places of remembrance to the future built by the new generations | Comune di Bucine | IT | 19.203,25 |
| REM-2008-006 | The Gate of Sorrow | Adazi District Council | LV | 28.304,00 |
| REM-2008-007 | Development of an Interactive Map of Stalinist Deportations | Latvijas Okupacijas muzeja biedriba (Occpation Museum Association) | LV | 39.000,00 |
| REM-2008-008 | Internet Community for Holocaust Remembrance | Stichting Hollandsche Schouwburg | NL | 52.525,00 |
| REM-2008-036 | Ost-westeuropaeisches Gedenkstaettenseminar | Fundacja Krzyzowa | PL | 24.922,30 |
| REM-2008-077 | Trasa Pamieci | Gmina Brzeszcze | PL | 15.228,00 |
| REM-2008-079 | From Individual Biographies to European Remembrance. International Oral History Programme for Education about the victims of Nacizm and Stalinism | KARTA Center Foundation | PL | 52.200,00 |
| REM-2008-090 | Nationalsozialismus und Holocaust- Actives gedenken in Europa | Goethe- Institut e V. Zweigstelle Goethe- Institut Krakau | PL | 16.149,00 |
| REM-2008-104 | Let's Talk About Freedom -Educational Project for Youth | Centre for Citizenship Education | PL | 14.955,32 |
| REM-2008-052 | Learning History through Past Experiences : Ordinary Citizens under the Surveillance of Securitate during the 1970s-1980s | The National Council for the Study of Securitate Archives (CNSAS) | RO | 26.450,00 |
|  |  |  |  | 1.710.787,68 € |

| Ref accusé réception dossier | Bénéficiaire | Town | Country | Website | Title of the project | Theme | Maximum grant amount € |
| --- | --- | --- | --- | --- | --- | --- | --- |
| REM 011 | Lasithi prefecture | Agios Nikolaos | GR | www.lasithinet.gr | Memories from the holocaust of Ierapetras western villages | Nazism, European values, freedom, democracy, respect for human rights | 13.800,00 |
| REM 016 | Comité international de Dachau | Paris | FR | www.kz-gedenkstaette-dachau.de | The transnational culture of Remembrance at the Dachau Concentration Camp Memorial site: Preservation of international victim testimonies for future generations | Nazism, mutual understanding, European values, freedom, respect for human rights, tolerance | 24.000,00 |
| REM 017 | Benchtours Productions Ltd | Edinburgh | UK | www.benchtours.com | The first to go | Nazism, equal opportunities, European values | 22.000,00 |
| REM 018* | Grenzlandmuseum Eichsfeld e.V. | Teistungen | DE | www.bildungsstaette-grenzlandmuseum-eichsfeld.de | Erinnerungskultur und regionale identität | Stalinism, Nazism; Active European Citizenship, Participation and Democracy; European Values, | 21.965,40 |
| REM 019 | Beth Shalom Ltd | Nottinghamshire | UK | www.holocaustcentre.net | History speaks | Nazism, Enlargement, European Values | 40.000,00 |
| REM 023 | YAHAD IN UNUM | Paris | FR | www.yadadinunum.org | Informing and raising awareness on the "Holocaust of bullets" in Europe | Nazism, Active Citizenship, Participation and Democracy, European values, | 39.596,41 |
| REM 024 | Leczynsko-Wlodawskie Lakeland Museum in Wlodawa | Wlodawa | PL | www.muzeum.wlodawa.metronet.pl | Meeting years later. Those who survived Sobihor (Befor we forget) | Nazism, Respect for human rights, tolerance | 31.524,86 |
| REM 037* | Teens, Kids & Cameras | Prague 1 | CZ | www.sunfilmproductions.com | Enemy's Daughters | Stalinism, Active European Citizenship, Participation and Democracy, Freedom, Democray, Respect for human rights, Tolerance | 25.000,00 |
| REM 038 | Centrum Edukacji Obywatelskiej | Warsaw | PL | www.ceo.org.pl | Lets talk about freedom - educational project for youth | Nazism, stalinism, freedom, democracy, respect for human rights, tolerance, cultural and linguistic diversity | 39.349,04 |
| REM 041 | Stiftung Brandenburgische Gedenkstätten | Oranienburg | DE | www.stiftung-bg.de | Zwangsprostituion im Kreig im 20. und angehenden 21.Jahrundert | Nazism, European Values, Respect for human rights | 36.600,00 |
| REM 050 | Association pour le Forum Culturel Autrichien | Marseille | FR |  | Musiques interdites par le Iième Reich | Nazism, European Values | 40.000,00 |
| REM 057 | Regional Museum in Tarnow | Tarnow | PL | www.muzeum.tarnow.pl | Memories saved from fire | Nazism, European values, freedom, democracy, respect for human rights | 15.675,00 |
| REM 058 | Pärnu David Oistrakh Festival | Pärnu | EE | www.oistfest.eee | Music of remembrance | Nazism, Stalinism, intercultural dialogue, European values, respect for human rights | 40.000,00 |
| REM 059 | Dachauer Forum e.V. | Dachau | DE | www.dachauer-forum.de | Internationale Wanderausstellung "Namen statt Numern" | Nazism, Active European citizenship, participation and Democracy, Futur of the European Union 50, Interculturel dialogue | 40.000,00 |
| REM 060 | Peace Bell Foundation | Rovereto (TN) | IT | www.fondazioneoperacampana.it | Memories at the crossroads of Fascism, Communism and Nazism. From the Italian-Yugoslav Border to a European International Border | Nazism, Stalinism, Active European Citizenship, Participation and Democracy, European values | 40.000,00 |
| REM 063 | The Forgotten Ones | Prague 1 | CZ | www.zmizeli-sousede.cz | The neighbours who dissappeard -Tribute to the Child Holocaust Victims | Nazism, respect for human rights, tolerance | 24.880,00 |
| REM 067 | Jewish Museum of Deportation and resistance | Mechelen | BE | www.cicb.be | Give them a face 2007 - 2008 | Nazism, European identity, respect for human rights | 20.000,00 |
| REM 069 | Holocaust Memorial Centre | Budapest | HU | www.hdke.hu | Commemoration of the victims of forced labour camps | Nazism, intercultural dialogue, European values, respect for human rights | 10.200,00 |
| REM 070 | Municipality of Sykies | Sykies, Thessaloniki | GR | www.sykies.gr | Forget us not | Nazism, European Integration, Old and new member states, European values, freedom, democracy, respect for human rights, networking | 39.981,80 |
| REM 072* | Foundation KOS | Warsaw | PL | www.fundacjakos.pl | Last Victims of Stalinism in Poland during the Martial Law period 1981-83 and their defenders | Stalinism, freedom, democracy, respect for human rights | 30.000,00 |
| REM 073 | The Roma People Association in Poland | Oswieçim | PL |  | The Roma - doomed for extermination |  | 38.178,60 |
| REM 076 | International Christian Embassy Jerusalem - Czech branch | Prague 10 | CZ | www.icej.cz | March of remembrance and hope | Nazism, Active European Citizenship, Participation and Democracy, Equal opportuntiesEuropean Values | 32.433,60 |
| REM 078* | Estonian Heritage Society | Tallinn | EE | www.muinsuskaitse.ee | Politcal repressions in Estonia in the 1940s and 1950s | Nazism, Stalilnism, European integration,freedom, democracy, respect for human rights, tolerance, solidarity | 40.000,00 |
| REM 092 | UPTER - Universita Popolare di Roma | Rome | IT | www.upter.it | Zagarolo, House of Memories and of the encounter amoung people | Nazism, Active European Citizenship, Participation and Democracy, European values, | 39.150,00 |
| REM 098 | Aktion Sühnezeichen Friedensdienste e.V. | Berlin | DE | www.asf-ev.de | Begegnen, Bewahren, Zukunft gestalten - Gemeinsames lebendiges Erinnern und Erhalten der Stätten nationalsozialistische Massenvernichtung, Dokumentation und Wahrung des Gedenkens an die Opfer | Nazim, Stalinism, Equal opportunities, European values, freedom, democracy, restpet for human rights | 40.000,00 |
| REM 100 | Municipality of Ypati | Ypati | GR | www.dimosypatis.gr | National network of young people from greek martyr cities and villages | Nazism, Active European Citizenship, Participation and Democracy, European values, | 40.000,00 |
| REM 101 | Akademia Muzycna im.I.J. Paderewskiego | Poznan | PL | www.amuz.poznan.pl | Music in Death Camps | Nazism, European values, respect for human rights, Cultural and lingiustic diversity, democracy, freedom | 24.000,00 |
| REM 103 | Verein Schloss Hartheim | Alkoven | AT | www.schloss-hartheim.at | Die nationalsozialistische 'Euthanasie' und ihre Opfer auf dem Gebiet der heutigen Tschechischen Republik 1939-1945 | Nazism, European Integration, Old and new member states, European values, freedom, democracy, equal opportunities, networking | 12.000,00 |
| REM 105 | Osrodek "Brama Grodzka - Teatr NN" | Lublin | PL | www.tnn.pl | Lights in the dark - Righteous among the nations | Nazism, Respect for human rights, tolerance | 40.000,00 |
| REM 108 | Comune di Massa | San Vito dei Normanni | IT | uffgab@comune.massa.ms.it | Pour ne pas oublier…: un pont sur la mémoire entre Italie et Pologne | Nazim, Active European Citizenship, Participation and Democracy, European values | 38.628,60 |
| REM 110 | Volkshochschule Hietzing | Wien | AT | www.vhs-hietzing.at | Die Farbe der Deportation. Tod ist Leben. Netzwerk Europa 08 | Nazism, European values, respect for human rights | 14.678,92 |
| REM 111 | Croacovitalia Foundation | Cracow | PL | www.cracovitalia.org | Out-live - testimony to the history | Nazism, intercultural dialogue, European Values | 25.000,00 |
| REM 112 | Associazione Aggregazione Coscentizzazione Movimentazione Socieale (ACMOS) | Torino | IT | www.acmos.net | www.remembrance.eu - Stories on Geography | Nazism, intercultural dialogue, European values | 36.750,00 |
| REM 115 | Liceo SC. St. "E.FERMI" | Bologna | IT | www.liceofermibo.net | The righteous and the remembrance of good | Nazism, Active European Citizenship, Participation and Democracy, Intercultural dialogue, European Values | 40.000,00 |
| REM 116 | Assocation 'SHAMIR' Rabbi Menahems Barkahans | Riga | Latvia | www.shamir.lv | To remeber not to happen again |  | 39.820,00 |
| REM 120 | The PSF Women's Centre Foundation | Warsaw | PL | www.feministki.org.pl | HERSTORY - Women's Memory of the Past | Nazism, Stalinisme, European values, equal opportunties, freedom, European integration, New and old member states | 24.000,00 |
| 36 |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 1.119.212,23 |

| Countries | Number of selected projects |
| --- | --- |
| PL | 9 |
| IT | 5 |
| DE | 4 |
| CZ | 3 |
| FR | 3 |
| GR | 3 |
| AT | 2 |
| EE | 2 |
| UK | 2 |
| BE | 1 |
| HU | 1 |
| LET | 1 |
| BG | 0 |
| CY | 0 |
| DK | 0 |
| ES | 0 |
| FI | 0 |
| IRL | 0 |
| LU | 0 |
| LIT | 0 |
| MT | 0 |
| NL | 0 |
| PT | 0 |
| RO | 0 |
| SE | 0 |
| SK | 0 |
| SLO | 0 |
| Total | 36 |

| REF. | COUNTRY | APPLICANT | TITLE | MAXIMUM GRANT AWARDED |
| --- | --- | --- | --- | --- |
| 08/0108 | HU | HEJCE LOCAL GOVERNMENT | The one thousand year old link | 149.508,44 € |
| 08/0105 | HU | BUDAPEST 18TH DISTRICT MUNICIPALITY | In Tune With Europe - Thematic Networking and Community Developmen | 131.097,45 € |
| 08/0110 | NL | STICHTING CULTUREEL DORP VAN EUROPA, 1999 WIJK AAN ZEE | Harvesting Cultural Village of Europe | 127.417,06 € |
| 08/0106 | BE | GEMEENTE MALLE INTERGEMEENTELIJK VERBROEDERINGSCOMITE' MALLE | Golden Bridge: Malle, Saint Savin 1960-2010 : 50 Years of Twinning | 138.034,71 € |
| 08/0109 | DE | STADT STEINHEIM | S-S-B-S-S Specchia-Steinheim-Busko-zdroj-Svevi Martin na Muri - Szigetszentmiklos | 108.734,67 € |
| 08/0111 | HU | KARCAG VAROS ONKORMANYZATA | Town Twinning Multi-Annual Projects for Networks of Twinned Towns | 78.146,44 € |
| 08/0114 | NL | MUNICIPALITY OF HAAREN | The Charter of European Rural Communities | 145.970,57 € |
| 08/0113 | DE | STADTVERWALTUNG FRANKFURT (ODER) | Vernetzung PPP-Strukturen Zwischen den Partnerstadten von Frankfurt (Oder) | 150.000,00 € |
| 08/0112 | HU | KISKUNMAJSA VAROS ONKORMANYZATA | The strenghten of Twinned Town relationship and searching of further cooperation | 68.212,54 € |

The figure is based on the calculations indicated in the grant applications, experience has shown that in practice the figure can be up to 30% lower.

The survey was carried out in February 2008.  An online questionnaire was sent to 632 Town-Twinning  beneficiaries, 169 of whom replied giving a response rate of 29%.

EACEA 07/2008 published on 25 April.

EACEA 26/2008 published on 10 September.

Some projects focus on several themes

According to the calculations in the applications, in 2008 there were 1.123 host towns and 2.507 invited towns compared to 896 host towns and 1.932 invited towns in 2007.

89 submitted and 52 selected in 2007.

An acceptance rate of 40%.

Compared to 108 in 2007.

Similar to 2007 when 126 were received.

In 2007 a total of 2252 applications were submitted and 1125 were selected.

Figure indicated in the grant applications